## 배선일정
서산 SKI 4,5 LINE 배선일정계획
배선 목록 |  | 7월 | [28 empty] | 8월
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
JIG IO | 계획 | bar: 7월 10 to 7월 11
시행
JIG SENSOR | 계획 | bar: 7월 10 to 7월 11
시행
전류 부하선 1,3,5 LANE | 계획 | 7월 17: 37; 7월 24: 37; 7월 31: 37
시행
전류 부하선 2,4,6 LANE | 계획 | 7월 20: 37; 7월 27: 37; 8월 3: 37
시행
VS 1LANE | 계획 | 7월 17: 37; 7월 24: 37; 7월 31: 37
시행
VS 2LANE | 계획 | 7월 20: 37; 7월 27: 37; 8월 3: 37
시행
CONTROL | 계획 | bar: 7월 11 to 7월 13
시행
MAIN POWER | 계획 | bar: 7월 13 to 7월 17
시행
CH MAIN | 계획 | bar: 7월 11 to 7월 13
시행
UPS | 계획 | bar: 7월 18
시행
FAN | 계획 | bar: 7월 18 to 7월 19
시행
TEMP, SMOKE | 계획 | bar: 7월 20 to 7월 21
시행
계획
시행

## JIG IO
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | JIG IO |  |  | 110+110 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | SMH200-03 | YST200 | JIG IO B/D DO6 | 2 | 2 | M SOL | YST025 | SMH250-03 | 24AWG 2C | WHITE | 350 | 80 / 80 | 220 |  | M SOL
2 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
3 | SMH200-03 | YST200 | JIG IO B/D DO7 | 2 | 2 | C SOL | YST025 | SMH250-03 | 24AWG 2C | WHITE | 350 | 80 / 80 | 220 |  | C SOL
4 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
5 | SMH200-03 | YST200 | JIG IO B/D DI6 | 1 | 1 | M L IN | YST025 | SMH250-03 | 24AWG 3C | RED | 1650 | 80 / 80 | 220 |  | M L IN
6 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
7 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
8 | SMH200-03 | YST200 | JIG IO B/D DI5 | 1 | 1 | M L OUT | YST025 | SMH250-03 | 24AWG 3C | RED | 1350 | 80 / 80 | 220 |  | M L OUT
9 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
10 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
11 | SMH200-03 | YST200 | JIG IO B/D DI8 | 1 | 1 | M R IN | YST025 | SMH250-03 | 24AWG 3C | RED | 1650 | 80 / 80 | 220 |  | M R IN
12 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
13 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
14 | SMH200-03 | YST200 | JIG IO B/D DI7 | 1 | 1 | M R OUT | YST025 | SMH250-03 | 24AWG 3C | RED | 1350 | 80 / 80 | 220 |  | M R OUT
15 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
16 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
17 | SMH200-03 | YST200 | JIG IO B/D DI17 | 1 | 1 | CL1 L O | YST025 | SMH250-03 | 24AWG 3C | RED | 2000 | 80 / 80 | 220 |  | CL1 L O | 길이수정
18 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
19 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
20 | SMH200-03 | YST200 | JIG IO B/D DI14 | 1 | 1 | CL1 L C | YST025 | SMH250-03 | 24AWG 3C | RED | 2000 | 80 / 80 | 220 |  | CL1 L C
21 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
22 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
23 | SMH200-03 | YST200 | JIG IO B/D DI15 | 1 | 1 | CL1 R O | YST025 | SMH250-03 | 24AWG 3C | RED | 2000 | 80 / 80 | 220 |  | CL1 R O
24 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
25 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
26 | SMH200-03 | YST200 | JIG IO B/D DI16 | 1 | 1 | CL1 R C | YST025 | SMH250-03 | 24AWG 3C | RED | 2000 | 80 / 80 | 220 |  | CL1 R C
27 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
28 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
29 | SMH200-03 | YST200 | JIG IO B/D DI17 | 1 | 1 | CL2 L O | YST025 | SMH250-03 | 24AWG 3C | RED | 2300 | 80 / 80 | 220 |  | CL2 L O
30 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
31 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
32 | SMH200-03 | YST200 | JIG IO B/D DI14 | 1 | 1 | CL2 L C | YST025 | SMH250-03 | 24AWG 3C | RED | 2300 | 80 / 80 | 220 |  | CL2 L C
33 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
34 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
35 | SMH200-03 | YST200 | JIG IO B/D DI15 | 1 | 1 | CL2 R O | YST025 | SMH250-03 | 24AWG 3C | RED | 2300 | 80 / 80 | 220 |  | CL2 R O
36 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
37 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
38 | SMH200-03 | YST200 | JIG IO B/D DI16 | 1 | 1 | CL2 R C | YST025 | SMH250-03 | 24AWG 3C | RED | 2300 | 80 / 80 | 220 |  | CL2 R C
39 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
40 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
41 | SMH200-03 | YST200 | JIG IO B/D DI29 | 1 | 1 | TR DE1 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2350 | 80 / 80 | 220 |  | TR DE1 L
42 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
43 | SMH200-03 | YST200 | JIG IO B/D DI31 | 1 | 1 | TR DE1 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2350 | 80 / 80 | 220 |  | TR DE1 D
44 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
45 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
46 | SMH200-03 | YST200 | JIG IO B/D DI30 | 1 | 1 | TR DE2 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2350 | 80 / 80 | 220 |  | TR DE2 L
47 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
48 | SMH200-03 | YST200 | JIG IO B/D DI32 | 1 | 1 | TR DE2 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2350 | 80 / 80 | 220 |  | TR DE2 D
49 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
50 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
51 | SMH200-03 | YST200 | JIG IO B/D DI33 | 1 | 1 | TR DE3 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2950 | 80 / 80 | 220 |  | TR DE3 L
52 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
53 | SMH200-03 | YST200 | JIG IO B/D DI35 | 1 | 1 | TR DE3 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2950 | 80 / 80 | 220 |  | TR DE3 D
54 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
55 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
56 | SMH200-03 | YST200 | JIG IO B/D DI34 | 1 | 1 | TR DE4 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2950 | 80 / 80 | 220 |  | TR DE4 L
57 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
58 | SMH200-03 | YST200 | JIG IO B/D DI36 | 1 | 1 | TR DE4 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2950 | 80 / 80 | 220 |  | TR DE4 D
59 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
60 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
61 | SMH200-03 | YST200 | JIG IO B/D DI29 | 1 | 1 | TR DE5 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2480 | 80 / 80 | 220 |  | TR DE5 L
62 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
63 | SMH200-03 | YST200 | JIG IO B/D DI31 | 1 | 1 | TR DE5 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2480 | 80 / 80 | 220 |  | TR DE5 D
64 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
65 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
66 | SMH200-03 | YST200 | JIG IO B/D DI30 | 1 | 1 | TR DE6 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 2480 | 80 / 80 | 220 |  | TR DE6 L
67 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
68 | SMH200-03 | YST200 | JIG IO B/D DI32 | 1 | 1 | TR DE6 D | YST025 | SMH250-03 | 24AWG 3C | RED | 2480 | 80 / 80 | 220 |  | TR DE6 D
69 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
70 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
71 | SMH200-03 | YST200 | JIG IO B/D DI33 | 1 | 1 | TR DE7 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 3080 | 80 / 80 | 220 |  | TR DE7 L
72 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
73 | SMH200-03 | YST200 | JIG IO B/D DI35 | 1 | 1 | TR DE7 D | YST025 | SMH250-03 | 24AWG 3C | RED | 3080 | 80 / 80 | 220 |  | TR DE7 D
74 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
75 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
76 | SMH200-03 | YST200 | JIG IO B/D DI34 | 1 | 1 | TR DE8 L | YST025 | SMH250-03 | 24AWG 2C | WHITE | 3080 | 80 / 80 | 220 |  | TR DE8 L
77 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK
78 | SMH200-03 | YST200 | JIG IO B/D DI36 | 1 | 1 | TR DE8 D | YST025 | SMH250-03 | 24AWG 3C | RED | 3080 | 80 / 80 | 220 |  | TR DE8 D
79 |  | YST200 |  | 2 | 2 |  | YST025 |  |  | WHITE
80 |  | YST200 |  | 3 | 3 |  | YST025 |  |  | BLACK

## JIG SENSOR
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | JIG SENSOR |  |  | 108+108+?? |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | SMP250-03 | SMT025 | JIG IO B/D DO6 | 2 |  | M SOL | + | DV3120 |  | RED | 250 |  | 216 |  | M SOL
2 |  | SMT025 |  | 3 |  |  | - |  |  | BLACK
3 | SMP250-03 | SMT025 | JIG IO B/D DO7 | 2 |  | C SOL | + | DV3120 |  | RED | 250 |  | 216 |  | C SOL
4 |  | SMT025 |  | 3 |  |  | - |  |  | BLACK
5 | SMP250-03 | SMT025 | JIG IO B/D DI6 | 1 |  | M L IN | + | PR08-2DN |  | BROWN | 250 | 80 | 216 |  | M L IN
6 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
7 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
8 | SMP250-03 | SMT025 | JIG IO B/D DI5 | 1 |  | M L OUT | + | PR12-4DN |  | BROWN | 250 | 80 | 216 |  | M L OUT
9 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
10 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
11 | SMP250-03 | SMT025 | JIG IO B/D DI8 | 1 |  | M R IN | + | PR08-2DN |  | BROWN | 250 | 80 | 216 |  | M R IN
12 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
13 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
14 | SMP250-03 | SMT025 | JIG IO B/D DI7 | 1 |  | M R OUT | + | PR12-4DN |  | BROWN | 250 | 80 | 216 |  | M R OUT
15 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
16 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
17 | SMP250-03 | SMT025 | JIG IO B/D DI17 | 1 |  | CL1 L O | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL1 L O
18 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
19 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
20 | SMP250-03 | SMT025 | JIG IO B/D DI14 | 1 |  | CL1 L C | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL1 L C
21 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
22 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
23 | SMP250-03 | SMT025 | JIG IO B/D DI15 | 1 |  | CL1 R O | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL1 R O
24 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
25 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
26 | SMP250-03 | SMT025 | JIG IO B/D DI16 | 1 |  | CL1 R C | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL1 R C
27 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
28 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
29 | SMP250-03 | SMT025 | JIG IO B/D DI17 | 1 |  | CL2 L O | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL2 L O
30 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
31 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
32 | SMP250-03 | SMT025 | JIG IO B/D DI14 | 1 |  | CL2 L C | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL2 L C
33 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
34 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
35 | SMP250-03 | SMT025 | JIG IO B/D DI15 | 1 |  | CL2 R O | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL2 R O
36 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
37 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
38 | SMP250-03 | SMT025 | JIG IO B/D DI16 | 1 |  | CL2 R C | + | SX670 |  | BROWN | 250 | 80 | 216 |  | CL2 R C
39 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
40 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
41 | SMP250-03 | SMT025 | JIG IO B/D DI29 | 1 |  | TR DE1 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE1 L
42 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
43 | SMP250-03 | SMT025 | JIG IO B/D DI31 | 1 |  | TR DE1 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE1 D
44 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
45 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
46 | SMP250-03 | SMT025 | JIG IO B/D DI30 | 1 |  | TR DE2 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE2 L
47 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
48 | SMP250-03 | SMT025 | JIG IO B/D DI32 | 1 |  | TR DE2 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE2 D
49 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
50 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
51 | SMP250-03 | SMT025 | JIG IO B/D DI33 | 1 |  | TR DE3 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE3 L
52 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
53 | SMP250-03 | SMT025 | JIG IO B/D DI35 | 1 |  | TR DE3 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE3 D
54 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
55 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
56 | SMP250-03 | SMT025 | JIG IO B/D DI34 | 1 |  | TR DE4 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE4 L
57 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
58 | SMP250-03 | SMT025 | JIG IO B/D DI36 | 1 |  | TR DE4 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE4 D
59 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
60 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
61 | SMP250-03 | SMT025 | JIG IO B/D DI29 | 1 |  | TR DE5 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE5 L
62 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
63 | SMP250-03 | SMT025 | JIG IO B/D DI31 | 1 |  | TR DE5 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE5 D
64 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
65 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
66 | SMP250-03 | SMT025 | JIG IO B/D DI30 | 1 |  | TR DE6 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE6 L
67 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
68 | SMP250-03 | SMT025 | JIG IO B/D DI32 | 1 |  | TR DE6 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE6 D
69 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
70 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
71 | SMP250-03 | SMT025 | JIG IO B/D DI33 | 1 |  | TR DE7 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE7 L
72 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
73 | SMP250-03 | SMT025 | JIG IO B/D DI35 | 1 |  | TR DE7 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE7 D
74 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
75 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
76 | SMP250-03 | SMT025 | JIG IO B/D DI34 | 1 |  | TR DE8 L | + | HT7-T11-L |  | BROWN | 250 | 80 | 216 |  | TR DE8 L
77 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE
78 | SMP250-03 | SMT025 | JIG IO B/D DI36 | 1 |  | TR DE8 D | + | HT7-T11-D |  | BROWN | 250 | 80 | 216 |  | TR DE8 D
79 |  | SMT025 |  | 2 |  |  | O |  |  | BLACK
80 |  | SMT025 |  | 3 |  |  | - |  |  | BLUE

## 전류부하선 I (1,3,5 Lane)
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY | [5 empty] | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | 전류부하선 I (1,3,5 Lane) |  |  | 37+37+37 | [5 empty] | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION | [5 empty] | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] |  | Color | Length [mm] | 2차 T/W [mm] | Q'ty | 세부1 | 세부2 |  |  |  | 450
1 |  | 16-5 O LUG | MAIN B/D 1,8 | I+1 |  | GRIPPER +1 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 1950 | 300/880 | 111 | I+1 |  | 2차 T/W | 1+ | 1500 | 1950
2 |  | 16-5 O LUG |  | I-1 |  | GRIPPER -1 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-1 | 양 I+29 | 트위스트 300mm 안하고 / 트위스트 하는 길이 | 1- | 3370 | 3820
3 |  | 16-5 O LUG |  | I+29 |  | GRIPPER +29 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 3820 |  | 111 | I+29 | 양 I-1 | 트위스트 시작지점에(300mm) 파란색 튜브로 라인구분 | 2+ | 1560 | 2010
4 |  | 16-5 O LUG |  | I-29 |  | GRIPPER -29 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-29 |  |  | 2- | 3480 | 3930
5 |  | 16-5 O LUG |  | I+2 |  | GRIPPER +2 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2010 | 300/940 | 111 | I+2 |  |  | 3+ | 1630 | 2080
6 |  | 16-5 O LUG |  | I-2 |  | GRIPPER -2 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-2 | 양 I+30 |  | 3- | 3590 | 4040
7 |  | 16-5 O LUG |  | I+30 |  | GRIPPER +30 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 3930 |  | 111 | I+30 | 양 I-2 |  | 4+ | 1690 | 2140
8 |  | 16-5 O LUG |  | I-30 |  | GRIPPER -30 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-30 |  |  | 4- | 3700 | 4150
9 |  | 16-5 O LUG |  | I+3 |  | GRIPPER +3 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2080 | 300/1010 | 111 | I+3 |  |  | 5+ | 1680 | 2130
10 |  | 16-5 O LUG |  | I-3 |  | GRIPPER -3 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-3 | 양 I+31 |  | 5- | 3730 | 4180
11 |  | 16-5 O LUG |  | I+31 |  | GRIPPER +31 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4040 |  | 111 | I+31 | 양 I-3 |  | 6+ | 1750 | 2200
12 |  | 16-5 O LUG |  | I-31 |  | GRIPPER -31 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-31 |  |  | 6- | 3840 | 4290
13 |  | 16-5 O LUG |  | I+4 |  | GRIPPER +4 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2140 | 300/1070 | 111 | I+4 |  |  | 7+ | 1810 | 2260
14 |  | 16-5 O LUG |  | I-4 |  | GRIPPER -4 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-4 | 양 I+32 |  | 7- | 3950 | 4400
15 |  | 16-5 O LUG |  | I+32 |  | GRIPPER +32 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4150 |  | 111 | I+32 | 양 I-4 |  | 8+ | 1880 | 2330
16 |  | 16-5 O LUG |  | I-32 |  | GRIPPER -32 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-32 |  |  | 8- | 4060 | 4510
17 |  | 16-5 O LUG | MAIN B/D 2,9 | I+5 |  | GRIPPER +5 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2130 | 300/1060 | 111 | I+5 |  |  | 9+ | 1870 | 2320
18 |  | 16-5 O LUG |  | I-5 |  | GRIPPER -5 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-5 | 양 I+33 |  | 9- | 4100 | 4550
19 |  | 16-5 O LUG |  | I+33 |  | GRIPPER +33 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4180 |  | 111 | I+33 | 양 I-5 |  | 10+ | 1930 | 2380
20 |  | 16-5 O LUG |  | I-33 |  | GRIPPER -33 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-33 |  |  | 10- | 4210 | 4660
21 |  | 16-5 O LUG |  | I+6 |  | GRIPPER +6 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2200 | 300/1130 | 111 | I+6 |  |  | 11+ | 1990 | 2440
22 |  | 16-5 O LUG |  | I-6 |  | GRIPPER -6 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-6 | 양 I+34 |  | 11- | 4310 | 4760
23 |  | 16-5 O LUG |  | I+34 |  | GRIPPER +34 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4290 |  | 111 | I+34 | 양 I-6 |  | 12+ | 2060 | 2510
24 |  | 16-5 O LUG |  | I-34 |  | GRIPPER -34 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-34 |  |  | 12- | 4420 | 4870
25 |  | 16-5 O LUG |  | I+7 |  | GRIPPER +7 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2260 | 300/1190 | 111 | I+7 |  |  | 13+ | 2050 | 2500
26 |  | 16-5 O LUG |  | I-7 |  | GRIPPER -7 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-7 | 양 I+35 |  | 13- | 4460 | 4910
27 |  | 16-5 O LUG |  | I+35 |  | GRIPPER +35 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4400 |  | 111 | I+35 | 양 I-7 |  | 14+ | 2110 | 2560
28 |  | 16-5 O LUG |  | I-35 |  | GRIPPER -35 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-35 |  |  | 14- | 4570 | 5020
29 |  | 16-5 O LUG |  | I+8 |  | GRIPPER +8 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2330 | 300/1260 | 111 | I+8 |  |  | 15+ | 2180 | 2630
30 |  | 16-5 O LUG |  | I-8 |  | GRIPPER -8 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-8 | 양 I+36 |  | 15- | 4680 | 5130
31 |  | 16-5 O LUG |  | I+36 |  | GRIPPER +36 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4510 |  | 111 | I+36 | 양 I-8 |  | 16+ | 2240 | 2690
32 |  | 16-5 O LUG |  | I-36 |  | GRIPPER -36 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-36 |  |  | 16- | 4790 | 5240
33 |  | 16-5 O LUG | MAIN B/D 3,10 | I+9 |  | GRIPPER +9 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2320 | 300/1250 | 111 | I+9 |  |  | 17+ | 2340 | 2790
34 |  | 16-5 O LUG |  | I-9 |  | GRIPPER -9 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-9 | 양 I+37 |  | 17- | 4700 | 5150
35 |  | 16-5 O LUG |  | I+37 |  | GRIPPER +37 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4550 |  | 111 | I+37 | 양 I-9 |  | 18+ | 2400 | 2850
36 |  | 16-5 O LUG |  | I-37 |  | GRIPPER -37 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-37 |  |  | 18- | 4720 | 5170
37 |  | 16-5 O LUG |  | I+10 |  | GRIPPER +10 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2380 | 300/1300 | 111 | I+10 |  |  | 19+ | 2460 | 2910
38 |  | 16-5 O LUG |  | I-10 |  | GRIPPER -10 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-10 | 양 I+38 |  | 19- | 4740 | 5190
39 |  | 16-5 O LUG |  | I+38 |  | GRIPPER +38 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4660 |  | 111 | I+38 | 양 I-10 |  | 20+ | 2530 | 2980
40 |  | 16-5 O LUG |  | I-38 |  | GRIPPER -38 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-38 |  |  | 20- | 4760 | 5210
41 |  | 16-5 O LUG |  | I+11 |  | GRIPPER +11 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2440 | 300/1370 | 111 | I+11 |  |  | 21+ | 2520 | 2970
42 |  | 16-5 O LUG |  | I-11 |  | GRIPPER -11 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-11 | 양 I+39 |  | 21- | 4700 | 5150
43 |  | 16-5 O LUG |  | I+39 |  | GRIPPER +39 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4760 |  | 111 | I+39 | 양 I-11 |  | 22+ | 2580 | 3030
44 |  | 16-5 O LUG |  | I-39 |  | GRIPPER -39 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-39 |  |  | 22- | 4720 | 5170
45 |  | 16-5 O LUG |  | I+12 |  | GRIPPER +12 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2510 | 300/1440 | 111 | I+12 |  |  | 23+ | 2650 | 3100
46 |  | 16-5 O LUG |  | I-12 |  | GRIPPER -12 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-12 | 양 I+40 |  | 23- | 4740 | 5190
47 |  | 16-5 O LUG |  | I+40 |  | GRIPPER +40 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4870 |  | 111 | I+40 | 양 I-12 |  | 24+ | 2710 | 3160
48 |  | 16-5 O LUG |  | I-40 |  | GRIPPER -40 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-40 |  |  | 24- | 4760 | 5210
49 |  | 16-5 O LUG | MAIN B/D 4,11 | I+13 |  | GRIPPER +13 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2500 | 300/1430 | 111 | I+13 |  |  | 25+ | 2700 | 3150
50 |  | 16-5 O LUG |  | I-13 |  | GRIPPER -13 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-13 | 양 I+41 |  | 25- | 4700 | 5150
51 |  | 16-5 O LUG |  | I+41 |  | GRIPPER +41 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 4910 |  | 111 | I+41 | 양 I-13 |  | 26+ | 2770 | 3220
52 |  | 16-5 O LUG |  | I-41 |  | GRIPPER -41 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-41 |  |  | 26- | 4730 | 5180
53 |  | 16-5 O LUG |  | I+14 |  | GRIPPER +14 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2560 | 300/1490 | 111 | I+14 |  |  | 27+ | 2830 | 3280
54 |  | 16-5 O LUG |  | I-14 |  | GRIPPER -14 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-14 | 양 I+42 |  | 27- | 4740 | 5190
55 |  | 16-5 O LUG |  | I+42 |  | GRIPPER +42 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5020 |  | 111 | I+42 | 양 I-14 |  | 28+ | 2890 | 3340
56 |  | 16-5 O LUG |  | I-42 |  | GRIPPER -42 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-42 |  |  | 28- | 4760 | 5210
57 |  | 16-5 O LUG |  | I+15 |  | GRIPPER +15 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2630 | 300/1560 | 111 | I+15
58 |  | 16-5 O LUG |  | I-15 |  | GRIPPER -15 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-15 | 양 I+43
59 |  | 16-5 O LUG |  | I+43 |  | GRIPPER +43 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5130 |  | 111 | I+43 | 양 I-15
60 |  | 16-5 O LUG |  | I-43 |  | GRIPPER -43 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-43
61 |  | 16-5 O LUG |  | I+16 |  | GRIPPER +16 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2690 | 300/1620 | 111 | I+16
62 |  | 16-5 O LUG |  | I-16 |  | GRIPPER -16 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-16 | 양 I+44
63 |  | 16-5 O LUG |  | I+44 |  | GRIPPER +44 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5240 |  | 111 | I+44 | 양 I-16
64 |  | 16-5 O LUG |  | I-44 |  | GRIPPER -44 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-44
65 |  | 16-5 O LUG | MAIN B/D 5,12 | I+17 |  | GRIPPER +17 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2790 | 300/1720 | 111 | I+17
66 |  | 16-5 O LUG |  | I-17 |  | GRIPPER -17 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-17 | 양 I+45
67 |  | 16-5 O LUG |  | I+45 |  | GRIPPER +45 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5150 |  | 111 | I+45 | 양 I-17
68 |  | 16-5 O LUG |  | I-45 |  | GRIPPER -45 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-45
69 |  | 16-5 O LUG |  | I+18 |  | GRIPPER +18 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2850 | 300/1780 | 111 | I+18
70 |  | 16-5 O LUG |  | I-18 |  | GRIPPER -18 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-18 | 양 I+46
71 |  | 16-5 O LUG |  | I+46 |  | GRIPPER +46 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5170 |  | 111 | I+46 | 양 I-18
72 |  | 16-5 O LUG |  | I-46 |  | GRIPPER -46 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-46
73 |  | 16-5 O LUG |  | I+19 |  | GRIPPER +19 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2910 | 300/1840 | 111 | I+19
74 |  | 16-5 O LUG |  | I-19 |  | GRIPPER -19 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-19 | 양 I+47
75 |  | 16-5 O LUG |  | I+47 |  | GRIPPER +47 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5190 |  | 111 | I+47 | 양 I-19
76 |  | 16-5 O LUG |  | I-47 |  | GRIPPER -47 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-47
77 |  | 16-5 O LUG |  | I+20 |  | GRIPPER +20 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2980 | 300/1910 | 111 | I+20
78 |  | 16-5 O LUG |  | I-20 |  | GRIPPER -20 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-20 | 양 I+48
79 |  | 16-5 O LUG |  | I+48 |  | GRIPPER +48 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5210 |  | 111 | I+48 | 양 I-20
80 |  | 16-5 O LUG |  | I-48 |  | GRIPPER -48 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-48
81 |  | 16-5 O LUG | MAIN B/D 6,13 | I+21 |  | GRIPPER +21 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 2970 | 300/1900 | 111 | I+21
82 |  | 16-5 O LUG |  | I-21 |  | GRIPPER -21 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-21 | 양 I+49
83 |  | 16-5 O LUG |  | I+49 |  | GRIPPER +49 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5150 |  | 111 | I+49 | 양 I-21
84 |  | 16-5 O LUG |  | I-49 |  | GRIPPER -49 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-49
85 |  | 16-5 O LUG |  | I+22 |  | GRIPPER +22 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3030 | 300/1960 | 111 | I+22
86 |  | 16-5 O LUG |  | I-22 |  | GRIPPER -22 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-22 | 양 I+50
87 |  | 16-5 O LUG |  | I+50 |  | GRIPPER +50 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5170 |  | 111 | I+50 | 양 I-22
88 |  | 16-5 O LUG |  | I-50 |  | GRIPPER -50 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-50
89 |  | 16-5 O LUG |  | I+23 |  | GRIPPER +23 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3100 | 300/2030 | 111 | I+23
90 |  | 16-5 O LUG |  | I-23 |  | GRIPPER -23 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-23 | 양 I+51
91 |  | 16-5 O LUG |  | I+51 |  | GRIPPER +51 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5190 |  | 111 | I+51 | 양 I-23
92 |  | 16-5 O LUG |  | I-51 |  | GRIPPER -51 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-51
93 |  | 16-5 O LUG |  | I+24 |  | GRIPPER +24 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3160 | 300/2090 | 111 | I+24
94 |  | 16-5 O LUG |  | I-24 |  | GRIPPER -24 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-24 | 양 I+52
95 |  | 16-5 O LUG |  | I+52 |  | GRIPPER +52 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5210 |  | 111 | I+52 | 양 I-24
96 |  | 16-5 O LUG |  | I-52 |  | GRIPPER -52 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-52
97 |  | 16-5 O LUG | MAIN B/D 7,14 | I+25 |  | GRIPPER +25 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3150 | 300/2080 | 111 | I+25
98 |  | 16-5 O LUG |  | I-25 |  | GRIPPER -25 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-25 | 양 I+53
99 |  | 16-5 O LUG |  | I+53 |  | GRIPPER +53 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5150 |  | 111 | I+53 | 양 I-25
100 |  | 16-5 O LUG |  | I-53 |  | GRIPPER -53 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-53
101 |  | 16-5 O LUG |  | I+26 |  | GRIPPER +26 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3220 | 300/2150 | 111 | I+26
102 |  | 16-5 O LUG |  | I-26 |  | GRIPPER -26 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-26 | 양 I+54
103 |  | 16-5 O LUG |  | I+54 |  | GRIPPER +54 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5180 |  | 111 | I+54 | 양 I-26
104 |  | 16-5 O LUG |  | I-54 |  | GRIPPER -54 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-54
105 |  | 16-5 O LUG |  | I+27 |  | GRIPPER +27 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3280 | 300/2210 | 111 | I+27
106 |  | 16-5 O LUG |  | I-27 |  | GRIPPER -27 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-27 | 양 I+55
107 |  | 16-5 O LUG |  | I+55 |  | GRIPPER +55 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5190 |  | 111 | I+55 | 양 I-27
108 |  | 16-5 O LUG |  | I-55 |  | GRIPPER -55 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-55
109 |  | 16-5 O LUG |  | I+28 |  | GRIPPER +28 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 3340 | 300/2270 | 111 | I+28
110 |  | 16-5 O LUG |  | I-28 |  | GRIPPER -28 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-28 | 양 I+56
111 |  | 16-5 O LUG |  | I+56 |  | GRIPPER +56 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 5210 |  | 111 | I+56 | 양 I-28
112 |  | 16-5 O LUG |  | I-56 |  | GRIPPER -56 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-56

## 전류부하선 I (2,4,6 Lane)
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY | [5 empty] | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | 전류부하선 I (2,4,6 Lane) |  |  | 37+37+37 | [5 empty] | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION | [5 empty] | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] |  | Color | Length [mm] | 2차 T/W [mm] | Q'ty | 세부1 | 세부2
1 |  | 16-5 O LUG | MAIN B/D 1,8 | I+1 |  | GRIPPER +1 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4300 | 300/1490 | 111 | I+1 |  | 2차 T/W
2 |  | 16-5 O LUG |  | I-1 |  | GRIPPER -1 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-1 | 양 I+29 | 트위스트 300mm 안하고 / 트위스트 하는 길이
3 |  | 16-5 O LUG |  | I+29 |  | GRIPPER +29 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2560 |  | 111 | I+29 | 양 I-1 | 트위스트 시작지점에(300mm) 빨간색 튜브로 라인구분
4 |  | 16-5 O LUG |  | I-29 |  | GRIPPER -29 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-29
5 |  | 16-5 O LUG |  | I+2 |  | GRIPPER +2 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4360 | 300/1510 | 111 | I+2
6 |  | 16-5 O LUG |  | I-2 |  | GRIPPER -2 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-2 | 양 I+30
7 |  | 16-5 O LUG |  | I+30 |  | GRIPPER +30 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2580 |  | 111 | I+30 | 양 I-2
8 |  | 16-5 O LUG |  | I-30 |  | GRIPPER -30 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-30
9 |  | 16-5 O LUG |  | I+3 |  | GRIPPER +3 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4430 | 300/1530 | 111 | I+3
10 |  | 16-5 O LUG |  | I-3 |  | GRIPPER -3 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-3 | 양 I+31
11 |  | 16-5 O LUG |  | I+31 |  | GRIPPER +31 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2600 |  | 111 | I+31 | 양 I-3
12 |  | 16-5 O LUG |  | I-31 |  | GRIPPER -31 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-31
13 |  | 16-5 O LUG |  | I+4 |  | GRIPPER +4 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4490 | 300/1550 | 111 | I+4
14 |  | 16-5 O LUG |  | I-4 |  | GRIPPER -4 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-4 | 양 I+32
15 |  | 16-5 O LUG |  | I+32 |  | GRIPPER +32 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2620 |  | 111 | I+32 | 양 I-4
16 |  | 16-5 O LUG |  | I-32 |  | GRIPPER -32 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-32
17 |  | 16-5 O LUG | MAIN B/D 2,9 | I+5 |  | GRIPPER +5 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4480 | 300/1490 | 111 | I+5
18 |  | 16-5 O LUG |  | I-5 |  | GRIPPER -5 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-5 | 양 I+33
19 |  | 16-5 O LUG |  | I+33 |  | GRIPPER +33 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2560 |  | 111 | I+33 | 양 I-5
20 |  | 16-5 O LUG |  | I-33 |  | GRIPPER -33 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-33
21 |  | 16-5 O LUG |  | I+6 |  | GRIPPER +6 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4540 | 300/1510 | 111 | I+6
22 |  | 16-5 O LUG |  | I-6 |  | GRIPPER -6 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-6 | 양 I+34
23 |  | 16-5 O LUG |  | I+34 |  | GRIPPER +34 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2580 |  | 111 | I+34 | 양 I-6
24 |  | 16-5 O LUG |  | I-34 |  | GRIPPER -34 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-34
25 |  | 16-5 O LUG |  | I+7 |  | GRIPPER +7 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4610 | 300/1530 | 111 | I+7
26 |  | 16-5 O LUG |  | I-7 |  | GRIPPER -7 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-7 | 양 I+35
27 |  | 16-5 O LUG |  | I+35 |  | GRIPPER +35 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2600 |  | 111 | I+35 | 양 I-7
28 |  | 16-5 O LUG |  | I-35 |  | GRIPPER -35 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-35
29 |  | 16-5 O LUG |  | I+8 |  | GRIPPER +8 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4670 | 300/1550 | 111 | I+8
30 |  | 16-5 O LUG |  | I-8 |  | GRIPPER -8 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-8 | 양 I+36
31 |  | 16-5 O LUG |  | I+36 |  | GRIPPER +36 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2620 |  | 111 | I+36 | 양 I-8
32 |  | 16-5 O LUG |  | I-36 |  | GRIPPER -36 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-36
33 |  | 16-5 O LUG | MAIN B/D 3,10 | I+9 |  | GRIPPER +9 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4660 | 300/1490 | 111 | I+9
34 |  | 16-5 O LUG |  | I-9 |  | GRIPPER -9 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-9 | 양 I+37
35 |  | 16-5 O LUG |  | I+37 |  | GRIPPER +37 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2560 |  | 111 | I+37 | 양 I-9
36 |  | 16-5 O LUG |  | I-37 |  | GRIPPER -37 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-37
37 |  | 16-5 O LUG |  | I+10 |  | GRIPPER +10 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4720 | 300/1510 | 111 | I+10
38 |  | 16-5 O LUG |  | I-10 |  | GRIPPER -10 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-10 | 양 I+38
39 |  | 16-5 O LUG |  | I+38 |  | GRIPPER +38 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2580 |  | 111 | I+38 | 양 I-10
40 |  | 16-5 O LUG |  | I-38 |  | GRIPPER -38 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-38
41 |  | 16-5 O LUG |  | I+11 |  | GRIPPER +11 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4790 | 300/1530 | 111 | I+11
42 |  | 16-5 O LUG |  | I-11 |  | GRIPPER -11 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-11 | 양 I+39
43 |  | 16-5 O LUG |  | I+39 |  | GRIPPER +39 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2600 |  | 111 | I+39 | 양 I-11
44 |  | 16-5 O LUG |  | I-39 |  | GRIPPER -39 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-39
45 |  | 16-5 O LUG |  | I+12 |  | GRIPPER +12 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4850 | 300/1550 | 111 | I+12
46 |  | 16-5 O LUG |  | I-12 |  | GRIPPER -12 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-12 | 양 I+40
47 |  | 16-5 O LUG |  | I+40 |  | GRIPPER +40 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2620 |  | 111 | I+40 | 양 I-12
48 |  | 16-5 O LUG |  | I-40 |  | GRIPPER -40 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-40
49 |  | 16-5 O LUG | MAIN B/D 4,11 | I+13 |  | GRIPPER +13 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5100 | 300/1490 | 111 | I+13
50 |  | 16-5 O LUG |  | I-13 |  | GRIPPER -13 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-13 | 양 I+41
51 |  | 16-5 O LUG |  | I+41 |  | GRIPPER +41 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2560 |  | 111 | I+41 | 양 I-13
52 |  | 16-5 O LUG |  | I-41 |  | GRIPPER -41 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-41
53 |  | 16-5 O LUG |  | I+14 |  | GRIPPER +14 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5080 | 300/1510 | 111 | I+14
54 |  | 16-5 O LUG |  | I-14 |  | GRIPPER -14 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-14 | 양 I+42
55 |  | 16-5 O LUG |  | I+42 |  | GRIPPER +42 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2580 |  | 111 | I+42 | 양 I-14
56 |  | 16-5 O LUG |  | I-42 |  | GRIPPER -42 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-42
57 |  | 16-5 O LUG |  | I+15 |  | GRIPPER +15 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5050 | 300/1530 | 111 | I+15
58 |  | 16-5 O LUG |  | I-15 |  | GRIPPER -15 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-15 | 양 I+43
59 |  | 16-5 O LUG |  | I+43 |  | GRIPPER +43 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2600 |  | 111 | I+43 | 양 I-15
60 |  | 16-5 O LUG |  | I-43 |  | GRIPPER -43 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-43
61 |  | 16-5 O LUG |  | I+16 |  | GRIPPER +16 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5030 | 300/1550 | 111 | I+16
62 |  | 16-5 O LUG |  | I-16 |  | GRIPPER -16 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-16 | 양 I+44
63 |  | 16-5 O LUG |  | I+44 |  | GRIPPER +44 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2620 |  | 111 | I+44 | 양 I-16
64 |  | 16-5 O LUG |  | I-44 |  | GRIPPER -44 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-44
65 |  | 16-5 O LUG | MAIN B/D 5,12 | I+17 |  | GRIPPER +17 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5030 | 300/1600 | 111 | I+17
66 |  | 16-5 O LUG |  | I-17 |  | GRIPPER -17 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-17 | 양 I+45
67 |  | 16-5 O LUG |  | I+45 |  | GRIPPER +45 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2670 |  | 111 | I+45 | 양 I-17
68 |  | 16-5 O LUG |  | I-45 |  | GRIPPER -45 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-45
69 |  | 16-5 O LUG |  | I+18 |  | GRIPPER +18 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 5010 | 300/1620 | 111 | I+18
70 |  | 16-5 O LUG |  | I-18 |  | GRIPPER -18 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-18 | 양 I+46
71 |  | 16-5 O LUG |  | I+46 |  | GRIPPER +46 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2690 |  | 111 | I+46 | 양 I-18
72 |  | 16-5 O LUG |  | I-46 |  | GRIPPER -46 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-46
73 |  | 16-5 O LUG |  | I+19 |  | GRIPPER +19 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4980 | 300/1640 | 111 | I+19
74 |  | 16-5 O LUG |  | I-19 |  | GRIPPER -19 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-19 | 양 I+47
75 |  | 16-5 O LUG |  | I+47 |  | GRIPPER +47 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2710 |  | 111 | I+47 | 양 I-19
76 |  | 16-5 O LUG |  | I-47 |  | GRIPPER -47 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-47
77 |  | 16-5 O LUG |  | I+20 |  | GRIPPER +20 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4960 | 300/1660 | 111 | I+20
78 |  | 16-5 O LUG |  | I-20 |  | GRIPPER -20 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-20 | 양 I+48
79 |  | 16-5 O LUG |  | I+48 |  | GRIPPER +48 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2730 |  | 111 | I+48 | 양 I-20
80 |  | 16-5 O LUG |  | I-48 |  | GRIPPER -48 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-48
81 |  | 16-5 O LUG | MAIN B/D 6,13 | I+21 |  | GRIPPER +21 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4850 | 300/1600 | 111 | I+21
82 |  | 16-5 O LUG |  | I-21 |  | GRIPPER -21 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-21 | 양 I+49
83 |  | 16-5 O LUG |  | I+49 |  | GRIPPER +49 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2670 |  | 111 | I+49 | 양 I-21
84 |  | 16-5 O LUG |  | I-49 |  | GRIPPER -49 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-49
85 |  | 16-5 O LUG |  | I+22 |  | GRIPPER +22 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4830 | 300/1620 | 111 | I+22
86 |  | 16-5 O LUG |  | I-22 |  | GRIPPER -22 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-22 | 양 I+50
87 |  | 16-5 O LUG |  | I+50 |  | GRIPPER +50 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2690 |  | 111 | I+50 | 양 I-22
88 |  | 16-5 O LUG |  | I-50 |  | GRIPPER -50 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-50
89 |  | 16-5 O LUG |  | I+23 |  | GRIPPER +23 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4800 | 300/1640 | 111 | I+23
90 |  | 16-5 O LUG |  | I-23 |  | GRIPPER -23 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-23 | 양 I+51
91 |  | 16-5 O LUG |  | I+51 |  | GRIPPER +51 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2710 |  | 111 | I+51 | 양 I-23
92 |  | 16-5 O LUG |  | I-51 |  | GRIPPER -51 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-51
93 |  | 16-5 O LUG |  | I+24 |  | GRIPPER +24 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4780 | 300/1660 | 111 | I+24
94 |  | 16-5 O LUG |  | I-24 |  | GRIPPER -24 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-24 | 양 I+52
95 |  | 16-5 O LUG |  | I+52 |  | GRIPPER +52 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2730 |  | 111 | I+52 | 양 I-24
96 |  | 16-5 O LUG |  | I-52 |  | GRIPPER -52 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-52
97 |  | 16-5 O LUG | MAIN B/D 7,14 | I+25 |  | GRIPPER +25 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4670 | 300/1600 | 111 | I+25
98 |  | 16-5 O LUG |  | I-25 |  | GRIPPER -25 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-25 | 양 I+53
99 |  | 16-5 O LUG |  | I+53 |  | GRIPPER +53 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2670 |  | 111 | I+53 | 양 I-25
100 |  | 16-5 O LUG |  | I-53 |  | GRIPPER -53 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-53
101 |  | 16-5 O LUG |  | I+26 |  | GRIPPER +26 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4650 | 300/1620 | 111 | I+26
102 |  | 16-5 O LUG |  | I-26 |  | GRIPPER -26 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-26 | 양 I+54
103 |  | 16-5 O LUG |  | I+54 |  | GRIPPER +54 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2690 |  | 111 | I+54 | 양 I-26
104 |  | 16-5 O LUG |  | I-54 |  | GRIPPER -54 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-54
105 |  | 16-5 O LUG |  | I+27 |  | GRIPPER +27 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4620 | 300/1640 | 111 | I+27
106 |  | 16-5 O LUG |  | I-27 |  | GRIPPER -27 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-27 | 양 I+55
107 |  | 16-5 O LUG |  | I+55 |  | GRIPPER +55 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2710 |  | 111 | I+55 | 양 I-27
108 |  | 16-5 O LUG |  | I-55 |  | GRIPPER -55 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-55
109 |  | 16-5 O LUG |  | I+28 |  | GRIPPER +28 | 16-5 O LUG |  | 16 Sq (1차 T/W) | 2차 T/W | WHITE | 4600 | 300/1660 | 111 | I+28
110 |  | 16-5 O LUG |  | I-28 |  | GRIPPER -28 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-28 | 양 I+56
|  | 16-5 O LUG |  | I+56 |  | GRIPPER +56 | 16-5 O LUG |  | 16 Sq (1차 T/W) |  | WHITE | 2730 |  | 111 | I+56 | 양 I-28
|  | 16-5 O LUG |  | I-56 |  | GRIPPER -56 | 16-5 O LUG |  |  |  | BLACK |  |  |  | I-56

## 전압센싱선 VS (1,3,5 Lane)
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | 전압센싱선 VS (1,3,5 Lane) |  |  | 37+37+37 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 1 | 1~16 | 1~16 | V-SENSING B/D J5 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 1860 | 100 / 100 | 111 |  | VS 1~4 | 파란색 튜브로 라인구분
2 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
3 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 2 | 1~16 | 1~16 | V-SENSING B/D J6 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2010 | 100 / 100 | 111 |  | VS 5~8
4 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
5 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 3 | 1~16 | 1~16 | V-SENSING B/D J7 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2160 | 100 / 100 | 111 |  | VS 9~12
6 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
7 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 4 | 1~16 | 1~16 | V-SENSING B/D J10 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2310 | 100 / 100 | 111 |  | VS 13~16
8 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
9 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 5 | 1~16 | 1~16 | V-SENSING B/D J11 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2560 | 100 / 100 | 111 |  | VS 17~20
10 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
11 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 6 | 1~16 | 1~16 | V-SENSING B/D J12 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2710 | 100 / 100 | 111 |  | VS 21~24
12 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
13 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 7 | 1~16 | 1~16 | V-SENSING B/D J13 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2860 | 100 / 100 | 111 |  | VS 25~28
14 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
15 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 1 | 1~16 | 1~16 | V-SENSING B/D J5 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3300 | 100 / 100 | 111 |  | VS 29~32
16 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
17 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 2 | 1~16 | 1~16 | V-SENSING B/D J6 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3450 | 100 / 100 | 111 |  | VS 33~36
18 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
19 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 3 | 1~16 | 1~16 | V-SENSING B/D J7 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3600 | 100 / 100 | 111 |  | VS 37~40
20 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
21 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 4 | 1~16 | 1~16 | V-SENSING B/D J10 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3750 | 100 / 100 | 111 |  | VS 41~44
22 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
23 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 5 | 1~16 | 1~16 | V-SENSING B/D J11 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 4000 | 100 / 100 | 111 |  | VS 45~48
24 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
25 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 6 | 1~16 | 1~16 | V-SENSING B/D J12 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 4150 | 100 / 100 | 111 |  | VS 49~52
26 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
27 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 7 | 1~16 | 1~16 | V-SENSING B/D J13 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 4300 | 100 / 100 | 111 |  | VS 53~56
28 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
29 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J17 | 1 | V+1 | GRIPPER +1 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1100 | 100 / 500 | 111 | VS + 1 | VS 1~14 (양 +29~42) | 세부 넘버링은 LUG 쪽만 작업
30 |  | HIF3-2022SCF |  | 2 | V-1 | GRIPPER -1 | 1.5-4 0 LUG | [6 empty] | VS - 1 |  | 파란색 튜브로 라인구분
31 |  | HIF3-2022SCF |  | 3 | V+2 | GRIPPER +2 | 1.5-4 0 LUG | [6 empty] | VS + 2 |  | 탈피길이 재수정
32 |  | HIF3-2022SCF |  | 4 | V-2 | GRIPPER -2 | 1.5-4 0 LUG | [6 empty] | VS - 2
33 |  | HIF3-2022SCF |  | 5 | V+3 | GRIPPER +3 | 1.5-4 0 LUG | [6 empty] | VS + 3
34 |  | HIF3-2022SCF |  | 6 | V-3 | GRIPPER -3 | 1.5-4 0 LUG | [6 empty] | VS - 3
35 |  | HIF3-2022SCF |  | 7 | V+4 | GRIPPER +4 | 1.5-4 0 LUG | [6 empty] | VS + 4
36 |  | HIF3-2022SCF |  | 8 | V-4 | GRIPPER -4 | 1.5-4 0 LUG | [6 empty] | VS - 4
37 |  | HIF3-2022SCF |  | 9 | V+5 | GRIPPER +5 | 1.5-4 0 LUG | [6 empty] | VS + 5
38 |  | HIF3-2022SCF |  | 10 | V-5 | GRIPPER -5 | 1.5-4 0 LUG | [6 empty] | VS - 5
39 |  | HIF3-2022SCF |  | 11 | V+6 | GRIPPER +6 | 1.5-4 0 LUG | [6 empty] | VS + 6
40 |  | HIF3-2022SCF |  | 12 | V-6 | GRIPPER -6 | 1.5-4 0 LUG | [6 empty] | VS - 6
41 |  | HIF3-2022SCF |  | 13 | V+7 | GRIPPER +7 | 1.5-4 0 LUG | [6 empty] | VS + 7
42 |  | HIF3-2022SCF |  | 14 | V-7 | GRIPPER -7 | 1.5-4 0 LUG | [6 empty] | VS - 7
43 |  | HIF3-2022SCF |  | 15 | V+8 | GRIPPER +8 | 1.5-4 0 LUG | [6 empty] | VS + 8
44 |  | HIF3-2022SCF |  | 16 | V-8 | GRIPPER -8 | 1.5-4 0 LUG | [6 empty] | VS - 8
45 |  | HIF3-2022SCF |  | 17 | V+9 | GRIPPER +9 | 1.5-4 0 LUG | [6 empty] | VS + 9
46 |  | HIF3-2022SCF |  | 18 | V-9 | GRIPPER -9 | 1.5-4 0 LUG | [6 empty] | VS - 9
47 |  | HIF3-2022SCF |  | 19 | V+10 | GRIPPER +10 | 1.5-4 0 LUG | [6 empty] | VS + 10
48 |  | HIF3-2022SCF |  | 20 | V-10 | GRIPPER -10 | 1.5-4 0 LUG | [6 empty] | VS - 10
49 |  | HIF3-2022SCF |  | 21 | V+11 | GRIPPER +11 | 1.5-4 0 LUG | [6 empty] | VS + 11
50 |  | HIF3-2022SCF |  | 22 | V-11 | GRIPPER -11 | 1.5-4 0 LUG | [6 empty] | VS - 11
51 |  | HIF3-2022SCF |  | 23 | V+12 | GRIPPER +12 | 1.5-4 0 LUG | [6 empty] | VS + 12
52 |  | HIF3-2022SCF |  | 24 | V-12 | GRIPPER -12 | 1.5-4 0 LUG | [6 empty] | VS - 12
53 |  | HIF3-2022SCF |  | 25 | V+13 | GRIPPER +13 | 1.5-4 0 LUG | [6 empty] | VS + 13
54 |  | HIF3-2022SCF |  | 26 | V-13 | GRIPPER -13 | 1.5-4 0 LUG | [6 empty] | VS - 13
55 |  | HIF3-2022SCF |  | 27 | V+14 | GRIPPER +14 | 1.5-4 0 LUG | [6 empty] | VS + 14
56 |  | HIF3-2022SCF |  | 28 | V-14 | GRIPPER -14 | 1.5-4 0 LUG | [6 empty] | VS - 14
57 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
58 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J16 | 1 | V+15 | GRIPPER +15 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1300 | 100 / 500 | 111 | VS + 15 | VS 15~28 (양 +43~56)
59 |  | HIF3-2022SCF |  | 2 | V-15 | GRIPPER -15 | 1.5-4 0 LUG | [6 empty] | VS - 15
60 |  | HIF3-2022SCF |  | 3 | V+16 | GRIPPER +16 | 1.5-4 0 LUG | [6 empty] | VS + 16
61 |  | HIF3-2022SCF |  | 4 | V-16 | GRIPPER -16 | 1.5-4 0 LUG | [6 empty] | VS - 16
62 |  | HIF3-2022SCF |  | 5 | V+17 | GRIPPER +17 | 1.5-4 0 LUG | [6 empty] | VS + 17
63 |  | HIF3-2022SCF |  | 6 | V-17 | GRIPPER -17 | 1.5-4 0 LUG | [6 empty] | VS - 17
64 |  | HIF3-2022SCF |  | 7 | V+18 | GRIPPER +18 | 1.5-4 0 LUG | [6 empty] | VS + 18
65 |  | HIF3-2022SCF |  | 8 | V-18 | GRIPPER -18 | 1.5-4 0 LUG | [6 empty] | VS - 18
66 |  | HIF3-2022SCF |  | 9 | V+19 | GRIPPER +19 | 1.5-4 0 LUG | [6 empty] | VS + 19
67 |  | HIF3-2022SCF |  | 10 | V-19 | GRIPPER -19 | 1.5-4 0 LUG | [6 empty] | VS - 19
68 |  | HIF3-2022SCF |  | 11 | V+20 | GRIPPER +20 | 1.5-4 0 LUG | [6 empty] | VS + 20
69 |  | HIF3-2022SCF |  | 12 | V-20 | GRIPPER -20 | 1.5-4 0 LUG | [6 empty] | VS - 20
70 |  | HIF3-2022SCF |  | 13 | V+21 | GRIPPER +21 | 1.5-4 0 LUG | [6 empty] | VS + 21
71 |  | HIF3-2022SCF |  | 14 | V-21 | GRIPPER -21 | 1.5-4 0 LUG | [6 empty] | VS - 21
72 |  | HIF3-2022SCF |  | 15 | V+22 | GRIPPER +22 | 1.5-4 0 LUG | [6 empty] | VS + 22
73 |  | HIF3-2022SCF |  | 16 | V-22 | GRIPPER -22 | 1.5-4 0 LUG | [6 empty] | VS - 22
74 |  | HIF3-2022SCF |  | 17 | V+23 | GRIPPER +23 | 1.5-4 0 LUG | [6 empty] | VS + 23
75 |  | HIF3-2022SCF |  | 18 | V-23 | GRIPPER -23 | 1.5-4 0 LUG | [6 empty] | VS - 23
76 |  | HIF3-2022SCF |  | 19 | V+24 | GRIPPER +24 | 1.5-4 0 LUG | [6 empty] | VS + 24
77 |  | HIF3-2022SCF |  | 20 | V-24 | GRIPPER -24 | 1.5-4 0 LUG | [6 empty] | VS - 24
78 |  | HIF3-2022SCF |  | 21 | V+25 | GRIPPER +25 | 1.5-4 0 LUG | [6 empty] | VS + 25
79 |  | HIF3-2022SCF |  | 22 | V-25 | GRIPPER -25 | 1.5-4 0 LUG | [6 empty] | VS - 25
80 |  | HIF3-2022SCF |  | 23 | V+26 | GRIPPER +26 | 1.5-4 0 LUG | [6 empty] | VS + 26
81 |  | HIF3-2022SCF |  | 24 | V-26 | GRIPPER -26 | 1.5-4 0 LUG | [6 empty] | VS - 26
82 |  | HIF3-2022SCF |  | 25 | V+27 | GRIPPER +27 | 1.5-4 0 LUG | [6 empty] | VS + 27
83 |  | HIF3-2022SCF |  | 26 | V-27 | GRIPPER -27 | 1.5-4 0 LUG | [6 empty] | VS - 27
84 |  | HIF3-2022SCF |  | 27 | V+28 | GRIPPER +28 | 1.5-4 0 LUG | [6 empty] | VS + 28
85 |  | HIF3-2022SCF |  | 28 | V-28 | GRIPPER -28 | 1.5-4 0 LUG | [6 empty] | VS - 28
86 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
87 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J17 | 1 | V+29 | GRIPPER +29 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1100 | 100 / 500 | 111 | VS + 29 | VS 29~42 (양 -1~14)
88 |  | HIF3-2022SCF |  | 2 | V-29 | GRIPPER -29 | 1.5-4 0 LUG | [6 empty] | VS - 29
89 |  | HIF3-2022SCF |  | 3 | V+30 | GRIPPER +30 | 1.5-4 0 LUG | [6 empty] | VS + 30
90 |  | HIF3-2022SCF |  | 4 | V-30 | GRIPPER -30 | 1.5-4 0 LUG | [6 empty] | VS - 30
91 |  | HIF3-2022SCF |  | 5 | V+31 | GRIPPER +31 | 1.5-4 0 LUG | [6 empty] | VS + 31
92 |  | HIF3-2022SCF |  | 6 | V-31 | GRIPPER -31 | 1.5-4 0 LUG | [6 empty] | VS - 31
93 |  | HIF3-2022SCF |  | 7 | V+32 | GRIPPER +32 | 1.5-4 0 LUG | [6 empty] | VS + 32
94 |  | HIF3-2022SCF |  | 8 | V-32 | GRIPPER -32 | 1.5-4 0 LUG | [6 empty] | VS - 32
95 |  | HIF3-2022SCF |  | 9 | V+33 | GRIPPER +33 | 1.5-4 0 LUG | [6 empty] | VS + 33
96 |  | HIF3-2022SCF |  | 10 | V-33 | GRIPPER -33 | 1.5-4 0 LUG | [6 empty] | VS - 33
97 |  | HIF3-2022SCF |  | 11 | V+34 | GRIPPER +34 | 1.5-4 0 LUG | [6 empty] | VS + 34
98 |  | HIF3-2022SCF |  | 12 | V-34 | GRIPPER -34 | 1.5-4 0 LUG | [6 empty] | VS - 34
99 |  | HIF3-2022SCF |  | 13 | V+35 | GRIPPER +35 | 1.5-4 0 LUG | [6 empty] | VS + 35
100 |  | HIF3-2022SCF |  | 14 | V-35 | GRIPPER -35 | 1.5-4 0 LUG | [6 empty] | VS - 35
101 |  | HIF3-2022SCF |  | 15 | V+36 | GRIPPER +36 | 1.5-4 0 LUG | [6 empty] | VS + 36
102 |  | HIF3-2022SCF |  | 16 | V-36 | GRIPPER -36 | 1.5-4 0 LUG | [6 empty] | VS - 36
103 |  | HIF3-2022SCF |  | 17 | V+37 | GRIPPER +37 | 1.5-4 0 LUG | [6 empty] | VS + 37
104 |  | HIF3-2022SCF |  | 18 | V-37 | GRIPPER -37 | 1.5-4 0 LUG | [6 empty] | VS - 37
105 |  | HIF3-2022SCF |  | 19 | V+38 | GRIPPER +38 | 1.5-4 0 LUG | [6 empty] | VS + 38
106 |  | HIF3-2022SCF |  | 20 | V-38 | GRIPPER -38 | 1.5-4 0 LUG | [6 empty] | VS - 38
107 |  | HIF3-2022SCF |  | 21 | V+39 | GRIPPER +39 | 1.5-4 0 LUG | [6 empty] | VS + 39
108 |  | HIF3-2022SCF |  | 22 | V-39 | GRIPPER -39 | 1.5-4 0 LUG | [6 empty] | VS - 39
109 |  | HIF3-2022SCF |  | 23 | V+40 | GRIPPER +40 | 1.5-4 0 LUG | [6 empty] | VS + 40
110 |  | HIF3-2022SCF |  | 24 | V-40 | GRIPPER -40 | 1.5-4 0 LUG | [6 empty] | VS - 40
111 |  | HIF3-2022SCF |  | 25 | V+41 | GRIPPER +41 | 1.5-4 0 LUG | [6 empty] | VS + 41
112 |  | HIF3-2022SCF |  | 26 | V-41 | GRIPPER -41 | 1.5-4 0 LUG | [6 empty] | VS - 41
113 |  | HIF3-2022SCF |  | 27 | V+42 | GRIPPER +42 | 1.5-4 0 LUG | [6 empty] | VS + 42
114 |  | HIF3-2022SCF |  | 28 | V-42 | GRIPPER -42 | 1.5-4 0 LUG | [6 empty] | VS - 42
115 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
116 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J16 | 1 | V+43 | GRIPPER +43 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1300 | 100 / 500 | 111 | VS + 43 | VS 43~56 (양 -15~28)
117 |  | HIF3-2022SCF |  | 2 | V-43 | GRIPPER -43 | 1.5-4 0 LUG | [6 empty] | VS - 43
118 |  | HIF3-2022SCF |  | 3 | V+44 | GRIPPER +44 | 1.5-4 0 LUG | [6 empty] | VS + 44
119 |  | HIF3-2022SCF |  | 4 | V-44 | GRIPPER -44 | 1.5-4 0 LUG | [6 empty] | VS - 44
120 |  | HIF3-2022SCF |  | 5 | V+45 | GRIPPER +45 | 1.5-4 0 LUG | [6 empty] | VS + 45
121 |  | HIF3-2022SCF |  | 6 | V-45 | GRIPPER -45 | 1.5-4 0 LUG | [6 empty] | VS - 45
122 |  | HIF3-2022SCF |  | 7 | V+46 | GRIPPER +46 | 1.5-4 0 LUG | [6 empty] | VS + 46
123 |  | HIF3-2022SCF |  | 8 | V-46 | GRIPPER -46 | 1.5-4 0 LUG | [6 empty] | VS - 46
124 |  | HIF3-2022SCF |  | 9 | V+47 | GRIPPER +47 | 1.5-4 0 LUG | [6 empty] | VS + 47
125 |  | HIF3-2022SCF |  | 10 | V-47 | GRIPPER -47 | 1.5-4 0 LUG | [6 empty] | VS - 47
126 |  | HIF3-2022SCF |  | 11 | V+48 | GRIPPER +48 | 1.5-4 0 LUG | [6 empty] | VS + 48
127 |  | HIF3-2022SCF |  | 12 | V-48 | GRIPPER -48 | 1.5-4 0 LUG | [6 empty] | VS - 48
128 |  | HIF3-2022SCF |  | 13 | V+49 | GRIPPER +49 | 1.5-4 0 LUG | [6 empty] | VS + 49
129 |  | HIF3-2022SCF |  | 14 | V-49 | GRIPPER -49 | 1.5-4 0 LUG | [6 empty] | VS - 49
130 |  | HIF3-2022SCF |  | 15 | V+50 | GRIPPER +50 | 1.5-4 0 LUG | [6 empty] | VS + 50
131 |  | HIF3-2022SCF |  | 16 | V-50 | GRIPPER -50 | 1.5-4 0 LUG | [6 empty] | VS - 50
132 |  | HIF3-2022SCF |  | 17 | V+51 | GRIPPER +51 | 1.5-4 0 LUG | [6 empty] | VS + 51
133 |  | HIF3-2022SCF |  | 18 | V-51 | GRIPPER -51 | 1.5-4 0 LUG | [6 empty] | VS - 51
134 |  | HIF3-2022SCF |  | 19 | V+52 | GRIPPER +52 | 1.5-4 0 LUG | [6 empty] | VS + 52
135 |  | HIF3-2022SCF |  | 20 | V-52 | GRIPPER -52 | 1.5-4 0 LUG | [6 empty] | VS - 52
136 |  | HIF3-2022SCF |  | 21 | V+53 | GRIPPER +53 | 1.5-4 0 LUG | [6 empty] | VS + 53
137 |  | HIF3-2022SCF |  | 22 | V-53 | GRIPPER -53 | 1.5-4 0 LUG | [6 empty] | VS - 53
138 |  | HIF3-2022SCF |  | 23 | V+54 | GRIPPER +54 | 1.5-4 0 LUG | [6 empty] | VS + 54
139 |  | HIF3-2022SCF |  | 24 | V-54 | GRIPPER -54 | 1.5-4 0 LUG | [6 empty] | VS - 54
140 |  | HIF3-2022SCF |  | 25 | V+55 | GRIPPER +55 | 1.5-4 0 LUG | [6 empty] | VS + 55
141 |  | HIF3-2022SCF |  | 26 | V-55 | GRIPPER -55 | 1.5-4 0 LUG | [6 empty] | VS - 55
142 |  | HIF3-2022SCF |  | 27 | V+56 | GRIPPER +56 | 1.5-4 0 LUG | [6 empty] | VS + 56
143 |  | HIF3-2022SCF |  | 28 | V-56 | GRIPPER -56 | 1.5-4 0 LUG | [6 empty] | VS - 56
144 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
145 | HIF3C-34D-2.54C | HIF3-2022SCF *28 |  | 1~28 | 1~28 |  | HIF3-2022SCF *28 | HIF3C-34D-2.54C | 22AWG 28C SHIELD |  | 2500 | 100 / 100 | 111 |  | COM 1 | 파란색 튜브로 라인구분
146 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD | 31 ~ 34 SHIELD |  | HIF3-2022SCF *4
147 | HIF3C-34D-2.54C | HIF3-2022SCF *28 |  | 1~28 | 1~28 |  | HIF3-2022SCF *28 | HIF3C-34D-2.54C | 22AWG 28C SHIELD |  | 2340 | 100 / 100 | 111 |  | COM 2
148 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD | 31 ~ 34 SHIELD |  | HIF3-2022SCF *4

## 전압센싱선 VS (2,4,6 Lane)
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | 전압센싱선 VS (2,4,6 Lane) |  |  | 37+37+37 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체 |  | 넘버링 수정
1 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 1 | 1~16 | 1~16 | V-SENSING B/D J5 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2210 | 100 / 100 | 111 |  | VS 1~4 |  | VS 29~32 | 빨간색 튜브로 라인구분
2 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
3 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 2 | 1~16 | 1~16 | V-SENSING B/D J6 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2250 | 100 / 100 | 111 |  | VS 5~8 |  | VS 33~36
4 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
5 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 3 | 1~16 | 1~16 | V-SENSING B/D J7 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2290 | 100 / 100 | 111 |  | VS 9~12 |  | VS 37~40
6 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
7 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 4 | 1~16 | 1~16 | V-SENSING B/D J10 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2330 | 100 / 100 | 111 |  | VS 13~16 |  | VS 41~44
8 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
9 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 5 | 1~16 | 1~16 | V-SENSING B/D J11 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2470 | 100 / 100 | 111 |  | VS 17~20 |  | VS 45~48
10 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
11 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 6 | 1~16 | 1~16 | V-SENSING B/D J12 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2510 | 100 / 100 | 111 |  | VS 21~24 |  | VS 49~52
12 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
13 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 7 | 1~16 | 1~16 | V-SENSING B/D J13 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 2550 | 100 / 100 | 111 |  | VS 25~28 |  | VS 53~56
14 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
15 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 1 | 1~16 | 1~16 | V-SENSING B/D J5 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3650 | 100 / 100 | 111 |  | VS 29~32 |  | VS 1~4
16 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
17 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 2 | 1~16 | 1~16 | V-SENSING B/D J6 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3690 | 100 / 100 | 111 |  | VS 33~36 |  | VS 5~8
18 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
19 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 3 | 1~16 | 1~16 | V-SENSING B/D J7 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3730 | 100 / 100 | 111 |  | VS 37~40 |  | VS 9~12
20 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
21 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 4 | 1~16 | 1~16 | V-SENSING B/D J10 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3770 | 100 / 100 | 111 |  | VS 41~44 |  | VS 13~16
22 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
23 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 5 | 1~16 | 1~16 | V-SENSING B/D J11 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3910 | 100 / 100 | 111 |  | VS 45~48 |  | VS 17~20
24 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
25 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 6 | 1~16 | 1~16 | V-SENSING B/D J12 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3950 | 100 / 100 | 111 |  | VS 49~52 |  | VS 21~24
26 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
27 | HIF3C-20D-2.54C | HIF3-2022SCF *18 | MAIN B/D 7 | 1~16 | 1~16 | V-SENSING B/D J13 | HIF3-2022SCF *18 | HIF3C-20D-2.54C | 22AWG 16C SHIELD |  | 3990 | 100 / 100 | 111 |  | VS 53~56 |  | VS 25~28
28 |  |  |  | 19,20 SHIELD | 19,20 SHIELD
29 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J17 | 1 | V+1 | GRIPPER +1 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1100 | 100 / 500 | 111 | VS + 1 | VS 1~14 (양 +29~42) | 세부 넘버링은 LUG 쪽만 작업
30 |  | HIF3-2022SCF |  | 2 | V-1 | GRIPPER -1 | 1.5-4 0 LUG | [6 empty] | VS - 1 |  | 빨간색 튜브로 라인구분
31 |  | HIF3-2022SCF |  | 3 | V+2 | GRIPPER +2 | 1.5-4 0 LUG | [6 empty] | VS + 2 |  | 탈피길이 재수정
32 |  | HIF3-2022SCF |  | 4 | V-2 | GRIPPER -2 | 1.5-4 0 LUG | [6 empty] | VS - 2
33 |  | HIF3-2022SCF |  | 5 | V+3 | GRIPPER +3 | 1.5-4 0 LUG | [6 empty] | VS + 3
34 |  | HIF3-2022SCF |  | 6 | V-3 | GRIPPER -3 | 1.5-4 0 LUG | [6 empty] | VS - 3
35 |  | HIF3-2022SCF |  | 7 | V+4 | GRIPPER +4 | 1.5-4 0 LUG | [6 empty] | VS + 4
36 |  | HIF3-2022SCF |  | 8 | V-4 | GRIPPER -4 | 1.5-4 0 LUG | [6 empty] | VS - 4
37 |  | HIF3-2022SCF |  | 9 | V+5 | GRIPPER +5 | 1.5-4 0 LUG | [6 empty] | VS + 5
38 |  | HIF3-2022SCF |  | 10 | V-5 | GRIPPER -5 | 1.5-4 0 LUG | [6 empty] | VS - 5
39 |  | HIF3-2022SCF |  | 11 | V+6 | GRIPPER +6 | 1.5-4 0 LUG | [6 empty] | VS + 6
40 |  | HIF3-2022SCF |  | 12 | V-6 | GRIPPER -6 | 1.5-4 0 LUG | [6 empty] | VS - 6
41 |  | HIF3-2022SCF |  | 13 | V+7 | GRIPPER +7 | 1.5-4 0 LUG | [6 empty] | VS + 7
42 |  | HIF3-2022SCF |  | 14 | V-7 | GRIPPER -7 | 1.5-4 0 LUG | [6 empty] | VS - 7
43 |  | HIF3-2022SCF |  | 15 | V+8 | GRIPPER +8 | 1.5-4 0 LUG | [6 empty] | VS + 8
44 |  | HIF3-2022SCF |  | 16 | V-8 | GRIPPER -8 | 1.5-4 0 LUG | [6 empty] | VS - 8
45 |  | HIF3-2022SCF |  | 17 | V+9 | GRIPPER +9 | 1.5-4 0 LUG | [6 empty] | VS + 9
46 |  | HIF3-2022SCF |  | 18 | V-9 | GRIPPER -9 | 1.5-4 0 LUG | [6 empty] | VS - 9
47 |  | HIF3-2022SCF |  | 19 | V+10 | GRIPPER +10 | 1.5-4 0 LUG | [6 empty] | VS + 10
48 |  | HIF3-2022SCF |  | 20 | V-10 | GRIPPER -10 | 1.5-4 0 LUG | [6 empty] | VS - 10
49 |  | HIF3-2022SCF |  | 21 | V+11 | GRIPPER +11 | 1.5-4 0 LUG | [6 empty] | VS + 11
50 |  | HIF3-2022SCF |  | 22 | V-11 | GRIPPER -11 | 1.5-4 0 LUG | [6 empty] | VS - 11
51 |  | HIF3-2022SCF |  | 23 | V+12 | GRIPPER +12 | 1.5-4 0 LUG | [6 empty] | VS + 12
52 |  | HIF3-2022SCF |  | 24 | V-12 | GRIPPER -12 | 1.5-4 0 LUG | [6 empty] | VS - 12
53 |  | HIF3-2022SCF |  | 25 | V+13 | GRIPPER +13 | 1.5-4 0 LUG | [6 empty] | VS + 13
54 |  | HIF3-2022SCF |  | 26 | V-13 | GRIPPER -13 | 1.5-4 0 LUG | [6 empty] | VS - 13
55 |  | HIF3-2022SCF |  | 27 | V+14 | GRIPPER +14 | 1.5-4 0 LUG | [6 empty] | VS + 14
56 |  | HIF3-2022SCF |  | 28 | V-14 | GRIPPER -14 | 1.5-4 0 LUG | [6 empty] | VS - 14
57 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
58 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J16 | 1 | V+15 | GRIPPER +15 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1300 | 100 / 500 | 111 | VS + 15 | VS 15~28 (양 +43~56)
59 |  | HIF3-2022SCF |  | 2 | V-15 | GRIPPER -15 | 1.5-4 0 LUG | [6 empty] | VS - 15
60 |  | HIF3-2022SCF |  | 3 | V+16 | GRIPPER +16 | 1.5-4 0 LUG | [6 empty] | VS + 16
61 |  | HIF3-2022SCF |  | 4 | V-16 | GRIPPER -16 | 1.5-4 0 LUG | [6 empty] | VS - 16
62 |  | HIF3-2022SCF |  | 5 | V+17 | GRIPPER +17 | 1.5-4 0 LUG | [6 empty] | VS + 17
63 |  | HIF3-2022SCF |  | 6 | V-17 | GRIPPER -17 | 1.5-4 0 LUG | [6 empty] | VS - 17
64 |  | HIF3-2022SCF |  | 7 | V+18 | GRIPPER +18 | 1.5-4 0 LUG | [6 empty] | VS + 18
65 |  | HIF3-2022SCF |  | 8 | V-18 | GRIPPER -18 | 1.5-4 0 LUG | [6 empty] | VS - 18
66 |  | HIF3-2022SCF |  | 9 | V+19 | GRIPPER +19 | 1.5-4 0 LUG | [6 empty] | VS + 19
67 |  | HIF3-2022SCF |  | 10 | V-19 | GRIPPER -19 | 1.5-4 0 LUG | [6 empty] | VS - 19
68 |  | HIF3-2022SCF |  | 11 | V+20 | GRIPPER +20 | 1.5-4 0 LUG | [6 empty] | VS + 20
69 |  | HIF3-2022SCF |  | 12 | V-20 | GRIPPER -20 | 1.5-4 0 LUG | [6 empty] | VS - 20
70 |  | HIF3-2022SCF |  | 13 | V+21 | GRIPPER +21 | 1.5-4 0 LUG | [6 empty] | VS + 21
71 |  | HIF3-2022SCF |  | 14 | V-21 | GRIPPER -21 | 1.5-4 0 LUG | [6 empty] | VS - 21
72 |  | HIF3-2022SCF |  | 15 | V+22 | GRIPPER +22 | 1.5-4 0 LUG | [6 empty] | VS + 22
73 |  | HIF3-2022SCF |  | 16 | V-22 | GRIPPER -22 | 1.5-4 0 LUG | [6 empty] | VS - 22
74 |  | HIF3-2022SCF |  | 17 | V+23 | GRIPPER +23 | 1.5-4 0 LUG | [6 empty] | VS + 23
75 |  | HIF3-2022SCF |  | 18 | V-23 | GRIPPER -23 | 1.5-4 0 LUG | [6 empty] | VS - 23
76 |  | HIF3-2022SCF |  | 19 | V+24 | GRIPPER +24 | 1.5-4 0 LUG | [6 empty] | VS + 24
77 |  | HIF3-2022SCF |  | 20 | V-24 | GRIPPER -24 | 1.5-4 0 LUG | [6 empty] | VS - 24
78 |  | HIF3-2022SCF |  | 21 | V+25 | GRIPPER +25 | 1.5-4 0 LUG | [6 empty] | VS + 25
79 |  | HIF3-2022SCF |  | 22 | V-25 | GRIPPER -25 | 1.5-4 0 LUG | [6 empty] | VS - 25
80 |  | HIF3-2022SCF |  | 23 | V+26 | GRIPPER +26 | 1.5-4 0 LUG | [6 empty] | VS + 26
81 |  | HIF3-2022SCF |  | 24 | V-26 | GRIPPER -26 | 1.5-4 0 LUG | [6 empty] | VS - 26
82 |  | HIF3-2022SCF |  | 25 | V+27 | GRIPPER +27 | 1.5-4 0 LUG | [6 empty] | VS + 27
83 |  | HIF3-2022SCF |  | 26 | V-27 | GRIPPER -27 | 1.5-4 0 LUG | [6 empty] | VS - 27
84 |  | HIF3-2022SCF |  | 27 | V+28 | GRIPPER +28 | 1.5-4 0 LUG | [6 empty] | VS + 28
85 |  | HIF3-2022SCF |  | 28 | V-28 | GRIPPER -28 | 1.5-4 0 LUG | [6 empty] | VS - 28
86 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
87 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J17 | 1 | V+29 | GRIPPER +29 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1100 | 100 / 500 | 111 | VS + 29 | VS 29~42 (양 -1~14)
88 |  | HIF3-2022SCF |  | 2 | V-29 | GRIPPER -29 | 1.5-4 0 LUG | [6 empty] | VS - 29
89 |  | HIF3-2022SCF |  | 3 | V+30 | GRIPPER +30 | 1.5-4 0 LUG | [6 empty] | VS + 30
90 |  | HIF3-2022SCF |  | 4 | V-30 | GRIPPER -30 | 1.5-4 0 LUG | [6 empty] | VS - 30
91 |  | HIF3-2022SCF |  | 5 | V+31 | GRIPPER +31 | 1.5-4 0 LUG | [6 empty] | VS + 31
92 |  | HIF3-2022SCF |  | 6 | V-31 | GRIPPER -31 | 1.5-4 0 LUG | [6 empty] | VS - 31
93 |  | HIF3-2022SCF |  | 7 | V+32 | GRIPPER +32 | 1.5-4 0 LUG | [6 empty] | VS + 32
94 |  | HIF3-2022SCF |  | 8 | V-32 | GRIPPER -32 | 1.5-4 0 LUG | [6 empty] | VS - 32
95 |  | HIF3-2022SCF |  | 9 | V+33 | GRIPPER +33 | 1.5-4 0 LUG | [6 empty] | VS + 33
96 |  | HIF3-2022SCF |  | 10 | V-33 | GRIPPER -33 | 1.5-4 0 LUG | [6 empty] | VS - 33
97 |  | HIF3-2022SCF |  | 11 | V+34 | GRIPPER +34 | 1.5-4 0 LUG | [6 empty] | VS + 34
98 |  | HIF3-2022SCF |  | 12 | V-34 | GRIPPER -34 | 1.5-4 0 LUG | [6 empty] | VS - 34
99 |  | HIF3-2022SCF |  | 13 | V+35 | GRIPPER +35 | 1.5-4 0 LUG | [6 empty] | VS + 35
100 |  | HIF3-2022SCF |  | 14 | V-35 | GRIPPER -35 | 1.5-4 0 LUG | [6 empty] | VS - 35
101 |  | HIF3-2022SCF |  | 15 | V+36 | GRIPPER +36 | 1.5-4 0 LUG | [6 empty] | VS + 36
102 |  | HIF3-2022SCF |  | 16 | V-36 | GRIPPER -36 | 1.5-4 0 LUG | [6 empty] | VS - 36
103 |  | HIF3-2022SCF |  | 17 | V+37 | GRIPPER +37 | 1.5-4 0 LUG | [6 empty] | VS + 37
104 |  | HIF3-2022SCF |  | 18 | V-37 | GRIPPER -37 | 1.5-4 0 LUG | [6 empty] | VS - 37
105 |  | HIF3-2022SCF |  | 19 | V+38 | GRIPPER +38 | 1.5-4 0 LUG | [6 empty] | VS + 38
106 |  | HIF3-2022SCF |  | 20 | V-38 | GRIPPER -38 | 1.5-4 0 LUG | [6 empty] | VS - 38
107 |  | HIF3-2022SCF |  | 21 | V+39 | GRIPPER +39 | 1.5-4 0 LUG | [6 empty] | VS + 39
108 |  | HIF3-2022SCF |  | 22 | V-39 | GRIPPER -39 | 1.5-4 0 LUG | [6 empty] | VS - 39
109 |  | HIF3-2022SCF |  | 23 | V+40 | GRIPPER +40 | 1.5-4 0 LUG | [6 empty] | VS + 40
110 |  | HIF3-2022SCF |  | 24 | V-40 | GRIPPER -40 | 1.5-4 0 LUG | [6 empty] | VS - 40
111 |  | HIF3-2022SCF |  | 25 | V+41 | GRIPPER +41 | 1.5-4 0 LUG | [6 empty] | VS + 41
112 |  | HIF3-2022SCF |  | 26 | V-41 | GRIPPER -41 | 1.5-4 0 LUG | [6 empty] | VS - 41
113 |  | HIF3-2022SCF |  | 27 | V+42 | GRIPPER +42 | 1.5-4 0 LUG | [6 empty] | VS + 42
114 |  | HIF3-2022SCF |  | 28 | V-42 | GRIPPER -42 | 1.5-4 0 LUG | [6 empty] | VS - 42
115 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
116 | HIF3C-34D-2.54C | HIF3-2022SCF | V-SENSING B/D J16 | 1 | V+43 | GRIPPER +43 | 1.5-4 0 LUG | LUG 납땜 | 22AWG 28C SHIELD |  | 1300 | 100 / 500 | 111 | VS + 43 | VS 43~56 (양 -15~28)
117 |  | HIF3-2022SCF |  | 2 | V-43 | GRIPPER -43 | 1.5-4 0 LUG | [6 empty] | VS - 43
118 |  | HIF3-2022SCF |  | 3 | V+44 | GRIPPER +44 | 1.5-4 0 LUG | [6 empty] | VS + 44
119 |  | HIF3-2022SCF |  | 4 | V-44 | GRIPPER -44 | 1.5-4 0 LUG | [6 empty] | VS - 44
120 |  | HIF3-2022SCF |  | 5 | V+45 | GRIPPER +45 | 1.5-4 0 LUG | [6 empty] | VS + 45
121 |  | HIF3-2022SCF |  | 6 | V-45 | GRIPPER -45 | 1.5-4 0 LUG | [6 empty] | VS - 45
122 |  | HIF3-2022SCF |  | 7 | V+46 | GRIPPER +46 | 1.5-4 0 LUG | [6 empty] | VS + 46
123 |  | HIF3-2022SCF |  | 8 | V-46 | GRIPPER -46 | 1.5-4 0 LUG | [6 empty] | VS - 46
124 |  | HIF3-2022SCF |  | 9 | V+47 | GRIPPER +47 | 1.5-4 0 LUG | [6 empty] | VS + 47
125 |  | HIF3-2022SCF |  | 10 | V-47 | GRIPPER -47 | 1.5-4 0 LUG | [6 empty] | VS - 47
126 |  | HIF3-2022SCF |  | 11 | V+48 | GRIPPER +48 | 1.5-4 0 LUG | [6 empty] | VS + 48
127 |  | HIF3-2022SCF |  | 12 | V-48 | GRIPPER -48 | 1.5-4 0 LUG | [6 empty] | VS - 48
128 |  | HIF3-2022SCF |  | 13 | V+49 | GRIPPER +49 | 1.5-4 0 LUG | [6 empty] | VS + 49
129 |  | HIF3-2022SCF |  | 14 | V-49 | GRIPPER -49 | 1.5-4 0 LUG | [6 empty] | VS - 49
130 |  | HIF3-2022SCF |  | 15 | V+50 | GRIPPER +50 | 1.5-4 0 LUG | [6 empty] | VS + 50
131 |  | HIF3-2022SCF |  | 16 | V-50 | GRIPPER -50 | 1.5-4 0 LUG | [6 empty] | VS - 50
132 |  | HIF3-2022SCF |  | 17 | V+51 | GRIPPER +51 | 1.5-4 0 LUG | [6 empty] | VS + 51
133 |  | HIF3-2022SCF |  | 18 | V-51 | GRIPPER -51 | 1.5-4 0 LUG | [6 empty] | VS - 51
134 |  | HIF3-2022SCF |  | 19 | V+52 | GRIPPER +52 | 1.5-4 0 LUG | [6 empty] | VS + 52
135 |  | HIF3-2022SCF |  | 20 | V-52 | GRIPPER -52 | 1.5-4 0 LUG | [6 empty] | VS - 52
136 |  | HIF3-2022SCF |  | 21 | V+53 | GRIPPER +53 | 1.5-4 0 LUG | [6 empty] | VS + 53
137 |  | HIF3-2022SCF |  | 22 | V-53 | GRIPPER -53 | 1.5-4 0 LUG | [6 empty] | VS - 53
138 |  | HIF3-2022SCF |  | 23 | V+54 | GRIPPER +54 | 1.5-4 0 LUG | [6 empty] | VS + 54
139 |  | HIF3-2022SCF |  | 24 | V-54 | GRIPPER -54 | 1.5-4 0 LUG | [6 empty] | VS - 54
140 |  | HIF3-2022SCF |  | 25 | V+55 | GRIPPER +55 | 1.5-4 0 LUG | [6 empty] | VS + 55
141 |  | HIF3-2022SCF |  | 26 | V-55 | GRIPPER -55 | 1.5-4 0 LUG | [6 empty] | VS - 55
142 |  | HIF3-2022SCF |  | 27 | V+56 | GRIPPER +56 | 1.5-4 0 LUG | [6 empty] | VS + 56
143 |  | HIF3-2022SCF |  | 28 | V-56 | GRIPPER -56 | 1.5-4 0 LUG | [6 empty] | VS - 56
144 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD
145 | HIF3C-34D-2.54C | HIF3-2022SCF *28 |  | 1~28 | 1~28 |  | HIF3-2022SCF *28 | HIF3C-34D-2.54C | 22AWG 28C SHIELD |  | 2700 | 100 / 100 | 111 |  | COM 1 | 빨간색 튜브로 라인구분
146 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD | 31 ~ 34 SHIELD |  | HIF3-2022SCF *4
147 | HIF3C-34D-2.54C | HIF3-2022SCF *28 |  | 1~28 | 1~28 |  | HIF3-2022SCF *28 | HIF3C-34D-2.54C | 22AWG 28C SHIELD |  | 2540 | 100 / 100 | 111 |  | COM 2
148 |  | HIF3-2022SCF *4 |  | 31 ~ 34 SHIELD | 31 ~ 34 SHIELD |  | HIF3-2022SCF *4

## CONTROL
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | CONTROL |  |  | 122+122 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | YH396-03V | YT396J | PS1 B/D J1 | 1 | 1 | PCPS | YT396J | YH396-03V | 1 Sq (T/W) | RED | 150 |  | 244 |  | PCPS
2 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | BLACK
3 | YH396-03V | YT396J | PS1 B/D J2 | 1 | L | DCP1 | 1.5-4 U LUG | 75-15 | 1 Sq (T/W) | RED | 850 |  | 244 | DCP1 220 L
4 |  | YT396J |  | 3 | N |  | 1.5-4 U LUG |  |  | BLACK |  |  |  | DCP1 220 N
5 | YH396-03V | YT396J | PS1 B/D J3 | 1 | L | DCP2 | 1.5-4 U LUG | 35-15 | 1 Sq (T/W) | RED | 960 |  | 244 | DCP2 220 L
6 |  | YT396J |  | 3 | N |  | 1.5-4 U LUG |  |  | BLACK |  |  |  | DCP2 220 N
7 | YH396-03V | YT396J | PS1 B/D J4 | 1 | L | DCP3 | 1.5-4 U LUG | 100-24 | 1 Sq (T/W) | RED | 740 |  | 244 | DCP3 220 L
8 |  | YT396J |  | 3 | N |  | 1.5-4 U LUG |  |  | BLACK |  |  |  | DCP3 220 N
9 |  | 1.5-4 U LUG | DCP 1,2,3 | FG |  |  | 1.5-4 U LUG | BRACKET | 1 Sq | GREEN | 100 |  | 732
10 | 같은 색상 쌍압착 | 5.5-4 U PG LUG *3 | DCP 1,2 | 15V | 1 | MASTER CONTROL B/D J23 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 520 |  | 244 | 15V | 15V CON
11 |  |  |  | AG | 2 |  | YT396J |  |  | WHITE |  |  |  | AG
12 |  |  |  | -15V | 3 |  | YT396J |  |  | BLUE |  |  |  | -15V
13 |  |  | DCP 1,2 | 15V | 1 | HV IN B/D 1 J3 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 780 |  | 244 | 15V | 15V HV IN1
14 |  |  |  | AG | 2 |  | YT396J |  |  | WHITE |  |  |  | AG
15 |  |  |  | -15V | 3 |  | YT396J |  |  | BLUE |  |  |  | -15V
16 |  |  |  | 15V | 1 |  | YT396J | YH396-03V | 1 Sq (T/W) | RED | 780 |  | 244 | 15V | 15V HV IN2
17 |  |  |  | AG | 2 |  | YT396J |  |  | WHITE |  |  |  | AG
18 |  |  |  | -15V | 3 |  | YT396J |  |  | BLUE |  |  |  | -15V
19 |  |  |  | 15V | 1 | HV IN B/D 2 J3 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 780 |  | 244 | 15V | 15V HV IN3
20 |  |  |  | AG | 2 |  | YT396J |  |  | WHITE |  |  |  | AG
21 |  |  |  | -15V | 3 |  | YT396J |  |  | BLUE |  |  |  | -15V
22 |  |  |  | 15V | 1 |  | YT396J | YH396-03V | 1 Sq (T/W) | RED | 780 |  | 244 | 15V | 15V HV IN4
23 |  |  |  | AG | 2 |  | YT396J |  |  | WHITE |  |  |  | AG
24 |  |  |  | -15V | 3 |  | YT396J |  |  | BLUE |  |  |  | -15V
25 | SMP396-03V | SMT396 | DCP 1,2 (WIRE TO WIRE) | 1 | 1 | HV IN B/D 1 J3 | YT396J | YH396-08V | 1 Sq (T/W) | RED | 800 |  | 244 |  | 15V HV IN1
26 |  | SMT396 |  | 2 | 4 |  | YT396J |  |  | WHITE
27 |  | SMT396 |  | 3 | 7 |  | YT396J |  |  | BLUE
28 | SMP396-03V | SMT396 |  | 1 | 1 | HV IN B/D 2 J3 | YT396J | YH396-08V | 1 Sq (T/W) | RED | 800 |  | 244 |  | 15V HV IN2
29 |  | SMT396 |  | 2 | 4 |  | YT396J |  |  | WHITE
30 |  | SMT396 |  | 3 | 7 |  | YT396J |  |  | BLUE
31 | SMP396-03V | SMT396 |  | 1 | 1 | HV IN B/D 3 J3 | YT396J | YH396-08V | 1 Sq (T/W) | RED | 1110 |  | 244 |  | 15V HV IN3
32 |  | SMT396 |  | 2 | 4 |  | YT396J |  |  | WHITE
33 |  | SMT396 |  | 3 | 7 |  | YT396J |  |  | BLUE
34 | SMP396-03V | SMT396 |  | 1 | 1 | HV IN B/D 4 J3 | YT396J | YH396-08V | 1 Sq (T/W) | RED | 1110 |  | 244 |  | 15V HV IN4
35 |  | SMT396 |  | 2 | 4 |  | YT396J |  |  | WHITE
36 |  | SMT396 |  | 3 | 7 |  | YT396J |  |  | BLUE
37 | 75-15 | 1.5-4 U LUG | DCP 1 | AG | AG | DCP 2 | 1.5-4 U LUG | 35-15 | 2.5 Sq | WHITE | 200 |  | 244
38 | 100-24 | 1.5-4 U LUG | DCP 3 | 24V | 1 | MASTER CONTROL B/D J14 | YT396J | YH396-04V | 1 Sq (T/W) | RED | 500 |  | 244 | 24V | 24V CON
39 |  | 1.5-4 U LUG |  | 24G | 3 |  | YT396J |  |  | GREEN |  |  |  | 24G
40 | 100-24 | 1.5-4 U LUG | DCP 3 | 24V | 1 | JIG IO B/D J5 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 900 |  | 244 | 24V | 24V JIG IO
41 |  | 1.5-4 U LUG |  | 24G | 3 |  | YT396J |  |  | GREEN |  |  |  | 24G
42 | SMP396-03V | SMT396 | DCP 3 (WIRE TO WIRE) | 1 | 1 | JIG IO B/D J5 | YT396J | YH396-04V | 1 Sq (T/W) | RED | 900 |  | 244 |  | 24V JIG IO
43 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | GREEN
44 | 35-15 | 1.5-4 U LUG |  | 15V | 1 | JIG I.O B/D J3 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 900 |  | 244 | 15V | 15V JIG IO
45 |  | 1.5-4 U LUG |  | 15G | 3 |  | YT396J |  |  | WHITE |  |  |  | 15G
46 | SMP396-03V | SMT396 | DCP 2 (WIRE TO WIRE) | 1 | 1 | JIG I.O B/D J3 | YT396J | YH396-04V | 1 Sq (T/W) | RED | 900 |  | 244 |  | 15V JIG IO
47 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | WHITE
48 | YH396-02V | YT396J | PS1 B/D J7 | 1 | 1 | MASTER CONTROL B/D J4 | YT396J | YH396-02V | 1 Sq (T/W) | YELLOW | 780 |  | 244 |  | PS ON
49 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
50 | YH396-09V | YT396J | PCPS | 1 | 1 | MASTER CONTROL B/D J2 | YT396J | YH396-09V | 1 Sq | YELLOW | 480 |  | 244 | SBC+12V
51 |  | YT396J |  | 2 | 2 |  | YT396J |  | 1 Sq | RED |  |  |  | SBC+5V
52 |  | YT396J |  | 3 | 3 |  | YT396J |  | 1 Sq | RED |  |  |  | SBC+5V
53 |  | YT396J |  | 4 | 4 |  | YT396J |  | 1 Sq | GREEN |  |  |  | DG
54 |  | YT396J |  | 5 | 5 |  | YT396J |  | 1 Sq | GREEN |  |  |  | DG
55 |  | YT396J |  | 6 | 6 |  | YT396J |  | 1 Sq | GREEN |  |  |  | DG
56 |  | YT396J |  | 7 | 7 |  | YT396J |  | 1 Sq | BLACK |  |  |  | SBC-12V
57 |  | YT396J |  | 8 | 8 |  | YT396J |  | 1 Sq | RED |  |  |  | 5VSB
58 |  | YT396J |  | 9 | 9 |  | YT396J |  | 1 Sq | WHITE |  |  |  | POWER ON
59 | CH0250-04P | CT0250 | SBC POWER | 1 | 1 | MASTER CONTROL B/D J12 | YT396J | YH396-04V | 0.5 Sq | RED | 150 |  | 244 |  | SBC POWER
60 |  | CT0250 |  | 2 | 2 |  | YT396J |  | 0.5 Sq | BLACK
61 |  | CT0250 |  | 3 | 3 |  | YT396J |  | 0.5 Sq | BLACK
62 |  | CT0250 |  | 4 | 4 |  | YT396J |  | 0.5 Sq | YELLOW
63 | HIF3BA-26PA-2.54DSA |  | CAN B/D J1 |  |  | MASTER CONTROL B/D J3 |  | HIF3BA-26PA-2.54DSA | FLAT CABLE 26C |  | 150 |  | 244
64 | YH396-04V | YT396J | CAN B/D J7 | 1 | 1 | MASTER CONTROL B/D J26 | YT396J | YH396-04V | 1 Sq (T/W) | RED | 650 |  | 244 |  | 5V CAN
65 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | BLACK

## MAIN POWER
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | MAIN POWER |  |  | 55+55 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | KH-60100-4P | 25-8 O LUG | MAIN TB1. 2 | R | R | U1, 2 MCCB INPUT | 25-8 O LUG | ABN103c 75A | 25 Sq | RED | 1250 |  | 220 |  | R220 MCCB
2 |  | 25-8 O LUG |  | S | S |  | 25-8 O LUG |  | 25 Sq | BLACK | 1250 |  | 220 |  | S220 MCCB
3 |  | 25-8 O LUG |  | T | T |  | 25-8 O LUG |  | 25 Sq | BLUE | 1250 |  | 220 |  | T220 MCCB
4 | ABN103c 75A | 25-8 O LUG | U1, 2 MCCB OUTPUT | R | R | U1, 2 ELCB INPUT | 25-8 O LUG | EBN103c 75A 500mA | 25 Sq | RED | 800 |  | 220 |  | R220 ELCB | 길이변경
5 |  | 25-8 O LUG |  | S | S |  | 25-8 O LUG |  | 25 Sq | BLACK | 850 |  | 220 |  | S220 ELCB
6 |  | 25-8 O LUG |  | T | T |  | 25-8 O LUG |  | 25 Sq | BLUE | 900 |  | 220 |  | T220 ELCB
7 |  | 2.5-8 O LUG * 3 | 23G471K * 3 |  |  | 3상 차단기용 |  |  | 1 Sq | BLACK | 120 |  | 220 SET
8 |  | 1.5-5 O LUG * 2 | 23G471K * 1 |  |  | 단상 차단기용 |  |  | 1 Sq | BLACK | 120 |  | 24 EA |  |  | TNR 작업 추가
9 | EBN103c 75A 500mA | 25-8 O LUG | U1, 2 ELCB OUTPUT | R | R | U1,2 INVERTER 1,2 INPUT | 10-4 O LUG | JWE-Q02-CAN 10KW | 10 Sq | RED | 620 |  | 220 |  | R220 INV 1
10 |  |  |  |  | R |  | 10-4 O LUG |  | 10 Sq | RED | 860 |  | 220 |  | R220 INV 2
11 |  | 25-8 O LUG |  | S | S |  | 10-4 O LUG |  | 10 Sq | BLACK | 620 |  | 220 |  | S220 INV 1
12 |  |  |  |  | S |  | 10-4 O LUG |  | 10 Sq | BLACK | 860 |  | 220 |  | S220 INV 2
13 |  | 25-8 O LUG |  | T | T |  | 10-4 O LUG |  | 10 Sq | BLUE | 620 |  | 220 |  | T220 INV 1
14 |  |  |  |  | T |  | 10-4 O LUG |  | 10 Sq | BLUE | 860 |  | 220 |  | T220 INV 2
15 | EBN103c 75A 500mA | 2.5-8 O LUG | U1, 2 ELCB OUTPUT | R | 1 | FAN B/D 2 INPUT | YT396J | YH396-03V | 1 Sq (T/W) | RED | 200 |  | 220 | R220 FAN 2 |  | 같은 색상 같은 하우징
16 |  |  |  |  | 1 | FAN B/D 1 INPUT | YT396J | YH396-03V |  | RED | 200 |  |  | R220 FAN 1
17 |  | 2.5-8 O LUG |  | S | 3 |  | YT396J |  |  | BLACK |  |  |  | S220 FAN 1
18 |  |  |  |  | 3 | FAN B/D 2 INPUT | YT396J | YH396-03V |  | BLACK | 200 |  |  | S220 FAN 2
19 | SMP396-03 | SMT396 | U1, 2 ELCB OUTPUT | 1 | 1 | FAN B/D 1 INPUT | YT396J | YH396-03V | 1 Sq (T/W) | RED | 600 |  | 220 | R220 FAN 1
20 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | BLACK |  |  |  | S220 FAN 1
21 | SMP396-03 | SMT396 | U1, 2 ELCB OUTPUT | 1 | 1 | FAN B/D 2 INPUT | YT396J | YH396-03V | 1 Sq (T/W) | RED | 910 |  | 220 | R220 FAN 2
22 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | BLACK |  |  |  | S220 FAN 2
23 | EBN103c 75A 500mA | 1.5-8 O LUG | U1, 2 ELCB OUTPUT | S | 1 | JIG FAN B/D1, 2 INPUT | YT396J | YH396-03V | 1 Sq (T/W) | BLACK | 200 |  | 220 | S220 JIG FAN
24 |  | 1.5-8 O LUG |  | T | 3 |  | YT396J |  |  | BLUE |  |  |  | T220 JIG FAN
25 | SMP396-03 | SMT396 | U1, 2 ELCB OUTPUT (WIRE TO WIRE) | 1 | 1 | JIG FAN B/D1, 2 INPUT (WIRE TO WIRE) | YT396J | YH396-03V | 1 Sq (T/W) | BLACK | 3200 |  | 220 | S220 JIG FAN
26 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | BLUE |  |  |  | T220 JIG FAN
27 | YH396-03V | YT396J | JIG FAN B/D2 | 1 | 1 | JIG FAN B/D1 INPUT | YT396J | YH396-03V | 0.5 Sq (T/W) | BLACK | 150 |  | 220 | S220 JIG FAN |  | 같은 색상 같은 하우징
28 | SMP396-03 | SMT396 | U1, 2 ELCB OUTPUT | 1 | [5 empty] | BLACK | 300 |  |  | S220 JIG FAN
29 |  | SMT396 |  | 3 | 3 |  | YT396J |  |  | BLUE |  |  |  | T220 JIG FAN
30 | YH396-03V | YT396J | JIG FAN B/D2 | 3 | [5 empty] | BLUE | 150 |  |  | T220 JIG FAN
31 | ABN103c 75A | 1.5-8 O LUG | U1, U2 MCCB OUTPUT | T | 1 | TRIP TB | 1.5-4 U LUG |  | 1 Sq | BLUE | 120 |  | 220
32 | KH-2201ER(2a) | 1.5-4 U LUG | EMG S/W | A | 2 |  | 1.5-4 U LUG |  | 0.75 Sq 2C | SKYBLUE | 1850 | 80 / 120 | 220 | TRIP A |  | 길이수정
33 |  | 1.5-4 U LUG |  | B | R | U1, U2 MCCB OUTPUT | 1.5-8 O LUG | ABN53c 40A |  | BROWN |  |  |  | TRIP B
34 | KH-2201ER(2a) | 1.5-4 U LUG | EMG S/W | C | 1 | DISPLAY B/D J16 | YT396J | YH396-02V | 22AWG 2C | WHITE | 1650 | 80 / 80 | 220 | EMG S/W 1
35 |  | 1.5-4 U LUG |  | D | 2 |  | YT396J |  |  | BLACK |  |  |  | EMG S/W 2
36 | YH396-06V | YT396J | DISPLAY B/D J1 | 1 | 1 | MASTER CONTROL B/D J1 | YT396J | YH396-06V | 22AWG 6C |  | 860 | 80 / 80 | 220 |  | SYS S/W
37 |  | YT396J |  | 2 | 2 |  | YT396J
38 |  | YT396J |  | 3 | 3 |  | YT396J
39 |  | YT396J |  | 4 | 4 |  | YT396J
40 |  | YT396J |  | 5 | 5 |  | YT396J
41 |  | YT396J |  | 6 | 6 |  | YT396J
42 | KH-60100-4P | 6-8 O LUG | MAIN TB1 | R | R | UPS ELCB INPUT | 6-5 O LUG | EBN33c 30A 500mA | 6 Sq (T/W) | RED | 1750 |  | 24 |  | R220 UPS ELCB
43 |  | 6-8 O LUG |  | S | S |  | 6-5 O LUG |  |  | BLACK |  |  |  |  | S220 UPS ELCB
44 |  | 6-8 O LUG |  | T | T |  | 6-5 O LUG |  |  | BLUE |  |  |  |  | T220 UPS ELCB
45 | EBN33c 30A 500mA | 6-5 O LUG | UPS ELCB OUTPUT | R | R | UPS INPUT | 15mm SOLDER | SURTD5000XLI | 6 Sq (T/W) | RED | 1700 |  | 8 |  | R220 UPS IN
46 |  | 6-5 O LUG |  | S | S |  | 15mm SOLDER |  |  | BLACK |  |  |  |  | S220 UPS IN
47 |  | 6-5 O LUG |  | S | S |  | 15mm SOLDER |  | 6 Sq (T/W) | BLACK | 1700 |  | 8 |  | S220 UPS IN
48 |  | 6-5 O LUG |  | T | T |  | 15mm SOLDER |  |  | BLUE |  |  |  |  | T220 UPS IN
49 |  | 6-5 O LUG |  | R | R |  | 15mm SOLDER |  | 6 Sq (T/W) | RED | 1700 |  | 8 |  | R220 UPS IN
50 |  | 6-5 O LUG |  | T | T |  | 15mm SOLDER |  |  | BLUE |  |  |  |  | T220 UPS IN
51 |  | 6-6 O LUG | BASE FG BUSBAR | FG | FG |  | 15mm SOLDER |  | 6 Sq | GREEN | 1650 |  | 24 |  | FG UPS
52 | KH-60100-4P | 25-8 O LUG | MAIN TB1 | R | R | MAIN TB2 | 25-8 O LUG | KH-60100-4P | 25 Sq | RED | 1400 |  | 110 |  | MAIN R
53 |  | 25-8 O LUG |  | S | S |  | 25-8 O LUG |  | 25 Sq | BLACK | 1400 |  | 110 |  | MAIN S
54 |  | 25-8 O LUG |  | T | T |  | 25-8 O LUG |  | 25 Sq | BLUE | 1400 |  | 110 |  | MAIN T
55 |  | 10-8 O LUG |  | FG | FG |  | 10-8 O LUG |  | 10 Sq | GREEN | 1400 |  | 110 |  | MAIN FG
56 | KH-60100-4P | 10-8 O LUG | MAIN TB1, 2 | FG | FG | U1, 2 FG BUSBAR | 10-6 O LUG |  | 10 Sq | GREEN | 530 |  | 220 |  | FG
57 |  | 4-4 O LUG | U1, 2 FG BUSBAR | FG | FG | CH MAIN BLOCK 1 | 4-5 O LUG |  | 4 Sq | GREEN | 1100 |  | 220 |  | FG S1
58 |  | 4-4 O LUG |  | FG | FG | CH MAIN BLOCK 2 | 4-5 O LUG |  | 4 Sq | GREEN | 700 |  | 220 |  | FG S2
59 |  | 4-4 O LUG |  | FG | FG | CH MAIN BLOCK 3 | 4-5 O LUG |  | 4 Sq | GREEN | 1410 |  | 220 |  | FG S3
60 |  | 4-4 O LUG |  | FG | FG | CH MAIN BLOCK 4 | 4-5 O LUG |  | 4 Sq | GREEN | 1010 |  | 220 |  | FG S4
61 |  | 4-4 O LUG |  | FG | FG | CONTROL BLOCK | 4-4 O LUG |  | 4 Sq | GREEN | 450 |  | 220 |  | FG CON
62 |  | 4-4 O LUG |  | FG | FG | INVERTER 1 | 4-5 O LUG |  | 4 Sq | GREEN | 550 |  | 220 |  | FG INV1
63 |  | 4-4 O LUG |  | FG | FG | INVERTER 2 | 4-5 O LUG |  | 4 Sq | GREEN | 790 |  | 220 |  | FG INV2
64 |  | 6-6 O LUG | U1 FG BUSBAR | FG | FG | BASE FG BUSBAR | 6-6 O LUG |  | 6 Sq | GREEN | 450 |  | 110 |  | FG COM
65 | SMH200-03 | YST200 | JIG IO B/D | 1 | + | KH-2201ER(2a) | 1.5-4 U LUG | EMG S/W | 24AWG 2C | WHITE | 500 | 80 / 80 | 220 |  | EMG LAMP | 배선추가
66 |  | YST200 |  | 2 | - |  | 1.5-4 U LUG |  |  | BLACK

## CH MAIN
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | CH MAIN |  |  | 110+110 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | JWE-Q02-CAN 10KW | 4-4 O LUG | INVERTER 1 OUTPUT | + | HV | HV IN B/D 1 | 4-5 O LUG | BR121 | 4 Sq (T/W) | RED | 1270 |  | 220 | HV1 |  | 길이수정함
2 |  | 4-4 O LUG |  | - | HG |  | 4-5 O LUG | BR121 |  | BLACK |  |  |  | HG1
3 | JWE-Q02-CAN 10KW | 4-4 O LUG | INVERTER 1 OUTPUT | + | HV | HV IN B/D 2 | 4-5 O LUG | BR121 | 4 Sq (T/W) | RED | 1200 |  | 220 | HV2
4 |  | 4-4 O LUG |  | - | HG |  | 4-5 O LUG | BR121 |  | BLACK |  |  |  | HG2
5 | JWE-Q02-CAN 10KW | 4-4 O LUG | INVERTER 2 OUTPUT | + | HV | HV IN B/D 3 | 4-5 O LUG | BR121 | 4 Sq (T/W) | RED | 1820 |  | 220 | HV3
6 |  | 4-4 O LUG |  | - | HG |  | 4-5 O LUG | BR121 |  | BLACK |  |  |  | HG3
7 | JWE-Q02-CAN 10KW | 4-4 O LUG | INVERTER 2 OUTPUT | + | HV | HV IN B/D 4 | 4-5 O LUG | BR121 | 4 Sq (T/W) | RED | 1750 |  | 220 | HV4
8 |  | 4-4 O LUG |  | - | HG |  | 4-5 O LUG | BR121 |  | BLACK |  |  |  | HG4
9 | YH396-03V | YT396J | HV IN B/D 2 J2 | 3 | 3 | HV IN B/D 1 J2 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 150 |  | 220 |  | 15V ISO 1 | 같은 색상 같은 하우징
10 | YH396-05V | YT396J | INVERTER 1 ISO | 1 | [5 empty] | RED | 1370
11 |  | YT396J |  | 3 | 1 |  | YT396J |  |  | WHITE
12 | YH396-03V | YT396J | HV IN B/D 2 J2 | 1 | [5 empty] | WHITE | 150
13 | YH396-03V | YT396J | HV IN B/D 4 J2 | 3 | 3 | HV IN B/D 3 J2 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 150 |  | 220 |  | 15V ISO 2 | 같은 색상 같은 하우징
14 | YH396-05V | YT396J | INVERTER 2 ISO | 1 | [5 empty] | RED | 1680
15 |  | YT396J |  | 3 | 1 |  | YT396J |  |  | WHITE
16 | YH396-03V | YT396J | HV IN B/D 4 J2 | 1 | [5 empty] | WHITE | 150
17 | YH396-05V | YT396J | HV IN B/D 1 J4 | 1 | 1 | MAIN B/D 1 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 400 |  | 440 |  | 15V MB1
18 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
19 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
20 | YH396-05V | YT396J | HV IN B/D 1 J5 | 1 | 1 | MAIN B/D 2 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 300 |  | 440 |  | 15V MB2
21 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
22 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
23 | YH396-05V | YT396J | HV IN B/D 1 J6 | 1 | 1 | MAIN B/D 3 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 200 |  | 440 |  | 15V MB3
24 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
25 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
26 | YH396-05V | YT396J | HV IN B/D 1 J7 | 1 | 1 | MAIN B/D 4 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 100 |  | 440 |  | 15V MB4
27 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
28 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
29 | YH396-05V | YT396J | HV IN B/D 2 J4 | 1 | 1 | MAIN B/D 5 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 200 |  | 440 |  | 15V MB5
30 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
31 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
32 | YH396-05V | YT396J | HV IN B/D 2 J5 | 1 | 1 | MAIN B/D 6 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 300 |  | 440 |  | 15V MB6
33 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
34 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
35 | YH396-05V | YT396J | HV IN B/D 2 J6 | 1 | 1 | MAIN B/D 7 J2 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 400 |  | 440 |  | 15V MB7
36 |  | YT396J |  | 3 | 3 |  | YT396J |  |  | WHITE
37 |  | YT396J |  | 5 | 5 |  | YT396J |  |  | BLUE
38 | RJ45 - STP |  | CAN B/D J2 |  |  | MAIN CONTROL B/D 1 |  | RJ45 - STP |  |  | 720 |  | 220 |  | MAIN CON 1
39 | RJ45 - STP |  | CAN B/D J2 |  |  | MAIN CONTROL B/D 1 |  | RJ45 - STP |  |  | 420 |  | 220 |  | MAIN CON 2
40 | RJ45 - STP |  | CAN B/D J3 |  |  | U1, 2 INVERTER |  | RJ45 - STP |  |  | 400 |  | 220 |  | INVERTER 1
41 | RJ45 - STP |  | CAN B/D J3 |  |  | U1, 2 INVERTER |  | RJ45 - STP |  |  | 320 |  | 220 |  | INVERTER 2
42 | RJ45 - STP |  | MAIN CONTROL B/D |  |  | MAIN CONTROL B/D |  | RJ45 - STP |  |  | 180 |  | 2200 |  |  | 수량 수정함
43 | RJ45 - STP |  | MAIN CONTROL B/D |  |  | MAIN CONTROL B/D |  | RJ45 - STP |  |  | 260 |  | 440
44 | RJ45 - STP |  | CAN B/D J10 |  |  | JIG IO B/D |  | RJ45 - STP |  |  | 1100 |  | 244 |  | JIG IO | 추가요청배선

## UPS
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | UPS |  |  | 12+12 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | SURTD5000XLI |  | UPS OUTPUT | L | L | 4구 CONCENT 1F | 1.5-4 U LUG | NCP2-22410 (위너스) | CAPCODE (사급/연장) | BROWN | 1000 | / 60 | 24 | 1F UPS220 L
2 |  |  |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 1F UPS220 N
3 |  |  |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 1F UPS220 FG
4 | SURTD5000XLI |  | UPS OUTPUT | L | L | 4구 CONCENT 2F | 1.5-4 U LUG | NCP2-22410 (위너스) | CAPCODE (사급/연장) | BROWN | 4980 | / 60 | 24 | 2F UPS220 L
5 |  |  |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 2F UPS220 N
6 |  |  |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 2F UPS220 FG
7 | SURTD5000XLI |  | UPS OUTPUT | L | L | 4구 CONCENT 3F | 1.5-4 U LUG | NCP2-22410 (위너스) | CAPCODE (사급/연장) | BROWN | 7660 | / 60 | 24 | 3F UPS220 L |  | 829 | 4980
8 |  |  |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 3F UPS220 N |  | 351 | 7660
9 |  |  |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 3F UPS220 FG |  | 190 | 10340
10 | SURTD5000XLI |  | UPS OUTPUT | L | L | 4구 CONCENT 4F | 1.5-4 U LUG | NCP2-22410 (위너스) | CAPCODE (사급/연장) | BROWN | 10340 | / 60 | 24 | 4F UPS220 L |  | 925 | 13020
11 |  |  |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 4F UPS220 N
12 |  |  |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 4F UPS220 FG
13 | SURTD5000XLI |  | UPS OUTPUT | L | L | 4구 CONCENT 5F | 1.5-4 U LUG | NCP2-22410 (위너스) | CAPCODE (사급/연장) | BROWN | 13020 | / 60 | 24 | 5F UPS220 L
14 |  |  |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 5F UPS220 N
15 |  |  |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 5F UPS220 FG
16 | KH-6060-4P | 1.5-6 O LUG | MAIN TB1 | L | L | 4구 CONCENT | 1.5-4 U LUG | NCP2-22410 (위너스) | 0.75 Sq 3C | BROWN | 1400 | / 60 | 96 | 검정색 수축튜브
17 |  | 1.5-6 O LUG |  | N | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | 검정색 수축튜브
18 |  | 1.5-6 O LUG |  | FG | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | 검정색 수축튜브
19 | NCP2-22410 (위너스) |  | 4구 CONCENT |  |  | U1 CONTROL |  |  | POWER CODE |  | 800 |  | 122 |  | CONTROL 1
20 | NCP2-22410 (위너스) |  | 4구 CONCENT |  |  | U1 CONTROL |  |  | POWER CODE |  | 1950 |  | 122 |  | CONTROL 2
21 | EBN33c 30A 500mA | 1.5-5 O LUG | UPS ELCB INPUT | R | 1 | AC FAIL B/D J5 | YT396J | YH396-05V | 1 Sq (T/W) | RED | 700 |  | 24 | R220
22 |  | 1.5-5 O LUG |  | S | 3 |  | YT396J |  |  | BLACK |  |  |  | S220
23 |  | 1.5-5 O LUG |  | T | 5 |  | YT396J |  |  | BLUE |  |  |  | T220
24 | NCP2-22410 (위너스) |  | 4구 CONCENT |  | L | UPS DCP | 1.5-4 U LUG | 35-24 | POWER CODE | BROWN | 200 | / 60 | 24 | UPS DCP L
25 |  |  |  |  | N |  | 1.5-4 U LUG |  |  | SKYBLUE |  |  |  | UPS DCP N
26 |  |  |  |  | FG |  | 1.5-4 U LUG |  |  | GREEN |  |  |  | UPS DCP FG
27 | 35-24 | 1.5-4 U LUG | UPS DCP | 24V | 1 | AC FAIL B/D J8 | YT396J | YH396-03V | 1 Sq (T/W) | RED | 200 |  | 24 | UPS FAIL 24V
28 |  | 1.5-4 U LUG |  | 24G | 3 |  | YT396J |  |  | GREEN |  |  |  | UPS FAIL 24G
29 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 1350 | 80 / 80 | 12 |  | AC FAIL U1
30 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
31 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 2500 | 80 / 80 | 12 |  | AC FAIL U2
32 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
33 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 3960 | 80 / 80 | 12 |  | AC FAIL U3
34 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
35 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 5110 | 80 / 80 | 12 |  | AC FAIL U4 | 1150 | 1460
36 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
37 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 6570 | 80 / 80 | 12 |  | AC FAIL U5
38 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
39 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 7720 | 80 / 80 | 12 |  | AC FAIL U6
40 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
41 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 9180 | 80 / 80 | 12 |  | AC FAIL U7
42 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
43 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 10330 | 80 / 80 | 12 |  | AC FAIL U8
44 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
45 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 11790 | 80 / 80 | 12 |  | AC FAIL U9
46 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
47 | YH396-02V | YT396J | AC FAIL B/D | 1 | 1 | MASTER CONTROL B/D J5 | YT396J | YH396-02V | 22AWG 2C | WHITE | 12940 | 80 / 80 | 12 |  | AC FAIL U10
48 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK

## FAN
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | FAN |  |  | 110+110 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 | YH396-02V | YT396J | MASTER CONTROL B/D J15 | 1 | 1 | FAN B/D 1 RUN | YT396J | YH396-02V | 22AWG 2C | WHITE | 860 | 80 / 80 | 220 |  | FAN ON 1
2 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
3 | YH396-02V | YT396J | MASTER CONTROL B/D J17 | 1 | 1 | FAN B/D 2 RUN | YT396J | YH396-02V | 22AWG 2C | WHITE | 1170 | 80 / 80 | 220 |  | FAN ON 2
4 |  | YT396J |  | 2 | 2 |  | YT396J |  |  | BLACK
5 | YH396-03V | YT396J | FAN B/D OUTPUT | 1 | 1 | FRONT FAN *5 | SMT396 | SMP396-03 | 1 Sq (T/W) | RED | 600 |  | 440 |  | FRONT FAN | 수량변경
6 |  | YT396J |  | 3 | 3 |  | SMT396 |  |  | BLACK
7 | YH396-03V | YT396J | FAN B/D OUTPUT | 1 | 1 | REAR FAN *10 | SMT396 | SMP396-03 | 1 Sq (T/W) | RED | 650 |  | 440 |  | REAR FAN
8 |  | YT396J |  | 3 | 3 |  | SMT396 |  |  | BLACK
9 |  | 1.5 2 W LUG | FAN4 | L | L | FAN5 | 1.5 2 W LUG |  | 1 Sq (T/W) | RED | 160 |  | 440 |  | FRONT FAN (하우징에만 넘버링)
10 |  |  |  |  | L | FAN3 | 1.5 2 W LUG |  |  | RED | 160
11 |  | 1.5 2 W LUG | FAN2 | L | [5 empty] | RED | 270
12 |  |  |  |  | L | FAN1 | 1.5 2 W LUG |  |  | RED | 160
13 | YH396-03V | YT396J | FRONT FAN BLOCK | 1 | [5 empty] | RED | 250
14 |  | YT396J |  | 3 | N | FAN1 | 1.5 2 W LUG |  |  | BLACK
15 |  | 1.5 2 W LUG | FAN2 | N | [5 empty] | BLACK | 160
16 |  |  |  |  | N | FAN3 | 1.5 2 W LUG |  |  | BLACK | 270
17 |  | 1.5 2 W LUG | FAN4 | N | [5 empty] | BLACK | 160
18 |  |  |  |  | N | FAN5 | 1.5 2 W LUG |  |  | BLACK | 160
19 |  | 1.5 2 W LUG | FAN10 | L | L | FAN9 | 1.5 2 W LUG |  | 1 Sq (T/W) | RED | 160 |  | 440 |  | REAR FAN (하우징에만 넘버링)
20 |  | 1.5 2 W LUG | FAN8 | L | [5 empty] | RED | 120
21 |  |  |  |  | L | FAN7 | 1.5 2 W LUG |  |  | RED | 160
22 |  | 1.5 2 W LUG | FAN6 | L | [5 empty] | RED | 120
23 |  |  |  |  | L | FAN5 | 1.5 2 W LUG |  |  | RED | 160
24 |  | 1.5 2 W LUG | FAN4 | L | [5 empty] | RED | 270
25 |  |  |  |  | L | FAN3 | 1.5 2 W LUG |  |  | RED | 160
26 |  | 1.5 2 W LUG | FAN2 | L | [5 empty] | RED | 120
27 |  |  |  |  | L | FAN1 | 1.5 2 W LUG |  |  | RED | 160
28 | YH396-03V | YT396J | REAR FAN BLOCK | 1 | [5 empty] | RED | 250
29 |  | YT396J |  | 3 | N | FAN1 | 1.5 2 W LUG |  |  | BLACK
30 |  | 1.5 2 W LUG | FAN2 | N | [5 empty] | BLACK | 160
31 |  |  |  |  | N | FAN3 | 1.5 2 W LUG |  |  | BLACK | 120
32 |  | 1.5 2 W LUG | FAN4 | N | [5 empty] | BLACK | 160
33 |  |  |  |  | N | FAN5 | 1.5 2 W LUG |  |  | BLACK | 270
34 |  | 1.5 2 W LUG | FAN6 | N | [5 empty] | BLACK | 160
35 |  |  |  |  | N | FAN7 | 1.5 2 W LUG |  |  | BLACK | 120
36 |  | 1.5 2 W LUG | FAN8 | N | [5 empty] | BLACK | 160
37 |  |  |  |  | N | FAN9 | 1.5 2 W LUG |  |  | BLACK | 120
38 |  | 1.5 2 W LUG | FAN10 | N | [5 empty] | BLACK | 160
39 |  | 1.5 2 W LUG | FAN2 | L | L | FAN1 | 1.5 2 W LUG |  |  | BLACK | 200 |  | 440 |  | JIG FAN 1 (하우징에만 넘버링) | JIG FAN 배선 수정
40 | YH396-03V | YT396J | JIG FAN BLOCK1 | 1 | [5 empty] | BLACK | 530
41 |  | YT396J |  | 3 | N | FAN1 | 1.5 2 W LUG |  |  | BLUE
42 |  | 1.5 2 W LUG | FAN2 | N | [5 empty] | BLUE | 200
39 |  | 1.5 2 W LUG | FAN2 | L | L | FAN1 | 1.5 2 W LUG |  |  | BLACK | 530 |  | 440 |  | JIG FAN 2 (하우징에만 넘버링)
40 | YH396-03V | YT396J | JIG FAN BLOCK2 | 1 | [5 empty] | BLACK | 380
41 |  | YT396J |  | 3 | N | FAN1 | 1.5 2 W LUG |  |  | BLUE
42 |  | 1.5 2 W LUG | FAN2 | N | [5 empty] | BLUE | 530
43 | SMH200-03 | YST200 | JIG IO B/D JIG FAN RUN 1 | 1 | 1 | JIG FAN B/D 1 RUN | YT396J | YH396-02V | 24AWG 2C | WHITE | 2200 | 80 / 80 | 220 |  | JIG FAN RUN 1
44 |  | YST200 |  | 2 | 2 |  | YT396J |  |  | BLACK
45 | SMH200-03 | YST200 | JIG IO B/D JIG FAN RUN 2 | 1 | 1 | JIG FAN B/D 2 RUN | YT396J | YH396-02V | 24AWG 2C | WHITE | 2200 | 80 / 80 | 220 |  | JIG FAN RUN 2
46 |  | YST200 |  | 2 | 2 |  | YT396J |  |  | BLACK

## TEMP, SMOKE
수주번호 |  |  |  | 제품명 |  |  | PRODUCT Q'TY |  |  |  |  | REV | 날짜 |  | 작성자
17FORRA005, 007 4, 5라인 |  |  |  | TEMP / SMOKE |  |  | 110+110 |  |  |  |  | 00 | 2017-06-19 |  | 박창순
NO. | START POSITION |  |  |  | END POSITION |  |  |  | WIRE SPECIFICATION |  |  |  |  | NUMBERING
| PARTS NO. | PIN NO. | POSITION | POSITION NO. | POSITION NO. | POSITION | PIN NO. | PARTS NO. | Tickness [AWG, Sq] | Color | Length [mm] | Coat Strip [mm] | Q'ty | 세부 | 전체
1 |  | 3mm SOLDER | TEMP SEN B/D | 1 | 1 | JIG IO B/D TEMP | SMT025 | SMP250-03 | 24AWG 3C | RED | 200 | 50 / 50 | 3520 |  | TH
2 |  | 3mm SOLDER |  | 2 | 2 |  | SMT025 |  |  | WHITE
3 |  | 3mm SOLDER |  | 3 | 3 |  | SMT025 |  |  | BLACK
4 | SMH250-03 | YST025 | TEMP SEN B/D 1 | 1 | 1 | JIG IO B/D TH1 | YST025 | SMH250-06 | 24AWG 6C |  | 2600 | 150 / 80 | 220 | TH1 (SMH250-03) | TH1,2 (SMH250-06)
5 |  | YST025 |  | 2 | 2 |  | YST025
6 |  | YST025 |  | 3 | 3 |  | YST025
7 | SMH250-03 | YST025 | TEMP SEN B/D 2 | 1 | 4 | JIG IO B/D TH2 | YST025 | [6 empty] | TH2 (SMH250-03)
8 |  | YST025 |  | 2 | 5 |  | YST025
9 |  | YST025 |  | 3 | 6 |  | YST025
10 | SMH250-03 | YST025 | TEMP SEN B/D 3 | 1 | 1 | JIG IO B/D TH3 | YST025 | SMH250-06 | 24AWG 6C |  | 2950 | 150 / 80 | 220 | TH3 (SMH250-03) | TH3,4 (SMH250-06)
11 |  | YST025 |  | 2 | 2 |  | YST025
12 |  | YST025 |  | 3 | 3 |  | YST025
13 | SMH250-03 | YST025 | TEMP SEN B/D 4 | 1 | 4 | JIG IO B/D TH4 | YST025 | [6 empty] | TH4 (SMH250-03)
14 |  | YST025 |  | 2 | 5 |  | YST025
15 |  | YST025 |  | 3 | 6 |  | YST025
16 | SMH250-03 | YST025 | TEMP SEN B/D 5 | 1 | 1 | JIG IO B/D TH5 | YST025 | SMH250-06 | 24AWG 6C |  | 2600 | 150 / 80 | 220 | TH5 (SMH250-03) | TH5,6 (SMH250-06)
17 |  | YST025 |  | 2 | 2 |  | YST025
18 |  | YST025 |  | 3 | 3 |  | YST025
19 | SMH250-03 | YST025 | TEMP SEN B/D 6 | 1 | 4 | JIG IO B/D TH6 | YST025 | [6 empty] | TH6 (SMH250-03)
20 |  | YST025 |  | 2 | 5 |  | YST025
21 |  | YST025 |  | 3 | 6 |  | YST025
22 | SMH250-03 | YST025 | TEMP SEN B/D 7 | 1 | 1 | JIG IO B/D TH7 | YST025 | SMH250-06 | 24AWG 6C |  | 2950 | 150 / 80 | 220 | TH7 (SMH250-03) | TH7,8 (SMH250-06)
23 |  | YST025 |  | 2 | 2 |  | YST025
24 |  | YST025 |  | 3 | 3 |  | YST025
25 | SMH250-03 | YST025 | TEMP SEN B/D 8 | 1 | 4 | JIG IO B/D TH8 | YST025 | [6 empty] | TH8 (SMH250-03)
26 |  | YST025 |  | 2 | 5 |  | YST025
27 |  | YST025 |  | 3 | 6 |  | YST025
28 | SMH250-03 | YST025 | TEMP SEN B/D 9 | 1 | 1 | JIG IO B/D TH1 | YST025 | SMH250-06 | 24AWG 6C |  | 2980 | 150 / 80 | 220 | TH9 (SMH250-03) | TH9,10 (SMH250-06) | 길이수정
29 |  | YST025 |  | 2 | 2 |  | YST025
30 |  | YST025 |  | 3 | 3 |  | YST025
31 | SMH250-03 | YST025 | TEMP SEN B/D 10 | 1 | 4 | JIG IO B/D TH2 | YST025 | [6 empty] | TH10 (SMH250-03)
32 |  | YST025 |  | 2 | 5 |  | YST025
33 |  | YST025 |  | 3 | 6 |  | YST025
34 | SMH250-03 | YST025 | TEMP SEN B/D 11 | 1 | 1 | JIG IO B/D TH3 | YST025 | SMH250-06 | 24AWG 6C |  | 3330 | 150 / 80 | 220 | TH11 (SMH250-03) | TH11,12 (SMH250-06)
35 |  | YST025 |  | 2 | 2 |  | YST025
36 |  | YST025 |  | 3 | 3 |  | YST025
37 | SMH250-03 | YST025 | TEMP SEN B/D 12 | 1 | 4 | JIG IO B/D TH4 | YST025 | [6 empty] | TH12 (SMH250-03)
38 |  | YST025 |  | 2 | 5 |  | YST025
39 |  | YST025 |  | 3 | 6 |  | YST025
40 | SMH250-03 | YST025 | TEMP SEN B/D 13 | 1 | 1 | JIG IO B/D TH5 | YST025 | SMH250-06 | 24AWG 6C |  | 2980 | 150 / 80 | 220 | TH13 (SMH250-03) | TH13,14 (SMH250-06)
41 |  | YST025 |  | 2 | 2 |  | YST025
42 |  | YST025 |  | 3 | 3 |  | YST025
43 | SMH250-03 | YST025 | TEMP SEN B/D 14 | 1 | 4 | JIG IO B/D TH6 | YST025 | [6 empty] | TH14 (SMH250-03)
44 |  | YST025 |  | 2 | 5 |  | YST025
45 |  | YST025 |  | 3 | 6 |  | YST025
46 | SMH250-03 | YST025 | TEMP SEN B/D 15 | 1 | 1 | JIG IO B/D TH7 | YST025 | SMH250-06 | 24AWG 6C |  | 3330 | 150 / 80 | 220 | TH15 (SMH250-03) | TH15,16 (SMH250-06)
47 |  | YST025 |  | 2 | 2 |  | YST025
48 |  | YST025 |  | 3 | 3 |  | YST025
49 | SMH250-03 | YST025 | TEMP SEN B/D 16 | 1 | 4 | JIG IO B/D TH8 | YST025 | [6 empty] | TH16 (SMH250-03)
50 |  | YST025 |  | 2 | 5 |  | YST025
51 |  | YST025 |  | 3 | 6 |  | YST025
52 | SD-50(가스 DNA) |  | SMOKE SENSOR | + | 1 | JIG IO B/D SMOKE | SMT025 | SMP250-03 | 사급 | RED | 250 | / 80 | 440 |  | SMOKE
53 |  |  |  | A | 2 |  | SMT025 |  |  | YELLOW
54 |  |  |  | COM, - | 3 |  | SMT025 |  |  | WHITE/ BLACK
55 | SMH250-03 | YST025 | SMOKE SENSOR | 1 | 1 | JIG IO B/D SMOKE 1 | YST200 | SMH200-03 | 24AWG 3C | RED | 2000 | 80 / 80 | 220 |  | SMOKE 1
56 |  | YST025 |  | 2 | 2 |  | YST200 |  |  | WHITE
57 |  | YST025 |  | 3 | 3 |  | YST200 |  |  | BLACK
58 | SMH250-03 | YST025 | SMOKE SENSOR | 1 | 1 | JIG IO B/D SMOKE 1 | YST200 | SMH200-03 | 24AWG 3C | RED | 3350 | 80 / 80 | 220 |  | SMOKE 2
59 |  | YST025 |  | 2 | 2 |  | YST200 |  |  | WHITE
60 |  | YST025 |  | 3 | 3 |  | YST200 |  |  | BLACK